## Slide 1
Delivery and margin review
2026-08 · 18 active engagements · 11 clients
Generated 2026-08-23
Scoring model v1.0
Run delivery-review-2026-08

## Slide 2
Portfolio summary
2026-08, active engagements, measured across the whole book
 | This period | Movement vs prior month
Active engagements | 18 | +0
Hours to date | 25,882.1 | +2,737.7
Ceiling hours | 44,390.0 | 
Portfolio burn | 58.3% | 
Revenue to date | 8,081,944 | 
Cost to date | 3,169,259 | 
Blended margin | 60.8% | -2.9pp
Mean health score | 83.4 | -1.2
In the green band | 13 of 18 | 
Blended margin is revenue less cost across the book, divided once. Fixed-price engagements take the fee as revenue; time and materials takes billable value at rate card.

## Slide 3
Margin by client
Blended across each client's active engagements, in percent
Chart: 
| Ashcombe Health Partners | Braemar Retail Corporation | Fernhollow Financial Trust | Lowmarsh Retail Partners | Merrivale Maritime Corporation | Northfield Municipal Group | Oakhaven Logistics Collective | Pentland Media Group | Quarrymoor Transit Partners | Stonebridge Energy Group | Thornbury Retail Partners
Margin % | 51 | 43.6 | 67.4 | 76.8 | 75.2 | 33.5 | 83.2 | -17.6 | 75 | 50.6 | 58.3
Lowest is Pentland Media Group at -17.6% across 1 engagement(s).

## Slide 4
Engagements at risk
8 of 10 engagements examined in detail, of 18 active
Engagement | Client | Burn | Margin | Health | Concentration | Ends
8 Regulatory Reporting Programme | Braemar Retail Corporation | 131.0% | 24.7% | 53.5 amber | 48.9% | 2027-05-12
9 Pricing Modernisation | Northfield Municipal Group | 124.5% | 33.5% | 59.5 amber | 54.1% | 2026-11-10
20 Inventory Implementation | Quarrymoor Transit Partners | 56.2% | 75.0% | 64.0 amber | 33.0% | 2027-04-16
22 Billing Platform Assessment | Fernhollow Financial Trust | 58.9% | 49.8% | 68.9 amber | 33.1% | 2027-01-25
5 Procurement Modernisation | Pentland Media Group | 65.1% | -17.6% | 69.0 amber | 24.8% | 2026-10-10
19 Grid Analytics Assessment | Thornbury Retail Partners | 86.9% | 51.6% | 76.6 green | 59.5% | 2026-10-10
25 Billing Platform Implementation | Stonebridge Energy Group | 80.6% | 50.2% | 76.6 green | 53.7% | 2026-10-25
15 Workforce Planning Programme | Ashcombe Health Partners | 76.1% | 50.7% | 94.4 green | 50.2% | 2026-10-16
Burn above 70% is amber and above 90% is red, the same thresholds the workbook applies. Ceilings are never re-baselined, so burn above 100% stays above 100%.

## Slide 5
RED · Regulatory Reporting Programme
Engagement 8 · Braemar Retail Corporation · fixed
Situation
Burn is 131.0% against a 1,020-hour ceiling, hours_remaining is -316.4, and projected_overrun_pct is 145.4% with 254 days remaining on a fixed fee of 274,176. Cost to date is 206,373 against margin of 24.7%.
Burn | 131.0% | Margin | 24.7%
Hours to date | 1,336.4 | Ceiling hours | 1,020.0
Hours remaining | -316.4 | Projected overrun | 145.4%
Health | 53.5 | Band | amber
Cause
not determinable from available data
Recommended action
Decide whether to seek a change order against SOW-2025-008 or stop work at the ceiling. Projection confidence is high.
Decision owner: engagement lead

## Slide 6
RED · Pricing Modernisation
Engagement 9 · Northfield Municipal Group · fixed
Situation
Burn is 124.5% against a 780-hour ceiling, hours_remaining is -191.2, and projected_overrun_pct is 78.8% with 71 days remaining. Fixed fee is 241,738; cost to date is 160,726 and margin is 33.5%.
Burn | 124.5% | Margin | 33.5%
Hours to date | 971.2 | Ceiling hours | 780.0
Hours remaining | -191.2 | Projected overrun | 78.8%
Health | 59.5 | Band | amber
Cause
not determinable from available data
Recommended action
Decide on a change order or a scope reduction for the remaining 71 days. Projection confidence is high.
Decision owner: engagement lead

## Slide 7
RED · Procurement Modernisation
Engagement 5 · Pentland Media Group · fixed
Situation
Margin is -17.6% on a fixed fee of 133,038 with cost to date of 156,516. Burn is 65.1% and health score fell 11.2 to 69.0. The 4-week run rate is 37.2% above this engagement's baseline.
Burn | 65.1% | Margin | -17.6%
Hours to date | 1,751.5 | Ceiling hours | 2,690.0
Hours remaining | 938.5 | Projected overrun | 0.0%
Health | 69.0 | Band | amber
Cause
not determinable from available data
Recommended action
Decide whether to continue delivery at negative margin or renegotiate the fee. Burn is inside the ceiling; the loss is on price, not hours.
Decision owner: engagement lead

## Slide 8
Data quality and caveats
2026-08, across the whole firm
Record quality | Count
Time entries in the period | 2,774
Filed after the period closed | 160 (5.8%)
No billable flag set | 2
Redundant rows: same person, engagement, day and hours | 1
Reporting coverage
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this pack, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
Engagement 25: 2 of the trailing 4 readable weeks have no time logged against this engagement
Figures come from the BizData tools and are reproduced in engagement-book-2026-08.xlsx. Scoring model v1.0.