## Summary
Delivery and margin review
Period | 2026-08
Run id | delivery-review-2026-08
Scoring model version | v1.0
Portfolio
Engagements in the book
Examined in detail
Ceiling hours
Hours to date
Ceiling amount
Over their ceiling
Above 70% burn
Not in the green band
Above 70% person concentration
Projections reported low confidence
Exceptions raised
Portfolio, as the tools measured it
Active engagements | 18
Clients | 11
In the green band | 13
Ceiling hours | 44390
Hours to date | 25882.1
Portfolio burn | 58.3
Revenue to date | 8081943.63
Cost to date | 3169258.7
Blended margin | 60.8
Mean health score | 83.4
Blended margin, movement vs prior month | -2.9
Mean health score, movement vs prior month | -1.2
Hours to date, movement vs prior month | 2737.7
Reporting coverage
Weeks below the coverage floor | 1
Lowest weekly reporting coverage | 16.7

## Engagements
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | ceiling_amount | person_concentration_pct | people_count | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | examined | hours_remaining | weekly_run_rate_4wk | weeks_counted | weeks_with_no_hours | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | run_rate_vs_baseline_pct | days_since_last_entry | late_entry_pct | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 |  | 420591.6 | 55.5 | 3 | 99.7 | green | -0.3 | payment_behaviour | yes | 1404.1 | 17.55 | 4 | 0 | 575.9 |  | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | -32 | 0 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 |  | 86.8 | 29.5 | 29 | 1.7
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 |  | 232180 | 46.2 | 3 | 98.3 | green | -0.9 | burn_trajectory | no
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 |  | 133038.43 | 24.8 | 5 | 69 | amber | -11.2 | margin | yes | 938.5 | 68.88 | 4 | 0 | 2145.1 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 37.2 | 0 | 3.4 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 |  | 87 | 44 | 41.1 | 6.9
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 |  | 393680 | 45 | 3 | 100 | green | 31.2 |  | no
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1336.4 |  | 274176 | 48.9 | 4 | 53.5 | amber | -3.8 | burn_trajectory | yes | -316.4 | 32.15 | 4 | 0 | 2503 |  | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | -1.7 | 3 | 2.1 | 42180.92 | 42180.92 | 351264.68 | 206372.8 | 393445.6 |  | 90 | 24.3 | 25.3 | -4
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 |  | 241737.6 | 54.1 | 2 | 59.5 | amber | -5.5 | burn_trajectory | yes | -191.2 | 41.73 | 4 | 0 | 1394.4 |  | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 12.5 | 0 | 3.1 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 |  | 87 | 32.8 | 31.3 | 4.5
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 |  | 1332713.2 | 44.7 | 3 | 73.1 | green | -6.6 | burn_trajectory | no
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 998.4 |  | 478040 | 85.4 | 2 | 99.9 | green | 0.4 | payment_behaviour | yes | 481.6 | 34.03 | 4 | 0 | 1115.1 |  | high | 4 readable weeks with time logged in every one, 9.9% of entries filed after the period closed | 1.3 | 0 | 9.9 | 261087.5 | 207099.5 | 21938.5 | 138190.2 | 283026 |  | 88.7 | 39.8 | 39.7 | 0.4
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 |  | 812800 | 63.6 | 3 | 89.1 | green | -0.2 | burn_trajectory | no
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 |  | 1069080 | 50.2 | 4 | 94.4 | green | 10.2 | burn_trajectory | yes | 845.5 | 71.18 | 4 | 0 | 3162.2 |  | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | -21.2 | 0 | 6.5 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 |  | 88.8 | 36.7 | 35.5 | 3.4
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 |  | 1955100 | 41.7 | 3 | 100 | green | 0.2 |  | no
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 |  | 217906.8 | 53.2 | 3 | 94.1 | green | -5.7 | burn_trajectory | no
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 |  | 262260 | 59.5 | 2 | 76.6 | green | -12.2 | burn_trajectory | yes | 123.2 | 29.88 | 4 | 0 | 987.5 |  | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 36.3 | 0 | 7.5 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 |  | 86.4 | 29.7 | 30.8 | -3.7
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 |  | 1154243.2 | 33 | 6 | 64 | amber | 0.8 | burn_trajectory | yes | 2119.3 | 110.78 | 4 | 0 | 6328.8 |  | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 17.8 | 0 | 7.8 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 |  | 89.1 | 55 | 51.7 | 6.5
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 |  | 443840 | 33.1 | 4 | 68.9 | amber | -7.2 | burn_trajectory | yes | 624.8 | 37.78 | 4 | 0 | 1688.5 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 3.3 | 0 | 3.4 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 |  | 90.9 | 46.2 | 44.1 | 4.7
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 |  | 455731.2 | 55.7 | 2 | 99.3 | green | -0.7 | payment_behaviour | no
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 |  | 688080 | 53.7 | 3 | 76.6 | green | -9.4 | reporting_gap | yes | 472.2 | 22.53 | 4 | 2 | 2144.8 |  | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | -46.6 | 24 | 0 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 |  | 87.4 | 39.8 | 39.7 | 0.4
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1108.6 |  | 482904.8 | 37.1 | 5 | 85.6 | green | -1.3 | burn_trajectory | no

## Time Detail
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | pct_active_reporting | firm_wide_gap
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11 | 100 | FALSE
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17 | 100 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24 | 94.1 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7 | 76.5 | FALSE
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37 | 100 | FALSE
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | 16.7 | TRUE
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51 | 94.4 | FALSE
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86 | 94.1 | FALSE
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17 | 76.5 | FALSE
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10 | 100 | FALSE
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22 | 94.4 | FALSE
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27 | 94.1 | FALSE
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4 | 76.5 | FALSE
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23 | 100 | FALSE
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49 | 94.4 | FALSE
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35 | 100 | FALSE
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19 | 94.4 | FALSE
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3 | 76.5 | FALSE
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52 | 100 | FALSE
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | 16.7 | TRUE
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67 | 94.4 | FALSE
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82 | 94.1 | FALSE
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12 | 76.5 | FALSE
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17 | 100 | FALSE
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16 | 94.4 | FALSE
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29 | 94.1 | FALSE
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9 | 76.5 | FALSE
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58 | 100 | FALSE
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60 | 94.4 | FALSE
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57 | 94.1 | FALSE
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10 | 76.5 | FALSE
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | 100 | FALSE
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | 94.4 | FALSE
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | 94.1 | FALSE
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | 76.5 | FALSE
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70 | 100 | FALSE
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66 | 94.4 | FALSE
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50 | 94.1 | FALSE
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15 | 76.5 | FALSE
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19 | 100 | FALSE
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57 | 94.4 | FALSE
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19 | 94.1 | FALSE
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4 | 76.5 | FALSE
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12 | 100 | FALSE
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3 | 94.4 | FALSE
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31 | 100 | FALSE
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27 | 94.4 | FALSE
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9 | 76.5 | FALSE
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84 | 100 | FALSE
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95 | 94.4 | FALSE
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99 | 94.1 | FALSE
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29 | 76.5 | FALSE
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48 | 100 | FALSE
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26 | 94.4 | FALSE
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39 | 94.1 | FALSE
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4 | 76.5 | FALSE
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13 | 100 | FALSE
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | 16.7 | TRUE
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16 | 94.4 | FALSE
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16 | 94.1 | FALSE
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46 | 94.4 | FALSE
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52 | 94.1 | FALSE
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18 | 76.5 | FALSE
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | 100 | FALSE
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | 94.4 | FALSE
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | 94.1 | FALSE
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | 76.5 | FALSE

## Exceptions
engagement_id | flag | situation | cause | recommended_action | decision_owner
8 | RED | Burn is 131.0% against a 1,020-hour ceiling, hours_remaining is -316.4, and projected_overrun_pct is 145.4% with 254 days remaining on a fixed fee of 274,176. Cost to date is 206,373 against margin of 24.7%. | not determinable from available data | Decide whether to seek a change order against SOW-2025-008 or stop work at the ceiling. Projection confidence is high. | engagement lead
9 | RED | Burn is 124.5% against a 780-hour ceiling, hours_remaining is -191.2, and projected_overrun_pct is 78.8% with 71 days remaining. Fixed fee is 241,738; cost to date is 160,726 and margin is 33.5%. | not determinable from available data | Decide on a change order or a scope reduction for the remaining 71 days. Projection confidence is high. | engagement lead
5 | RED | Margin is -17.6% on a fixed fee of 133,038 with cost to date of 156,516. Burn is 65.1% and health score fell 11.2 to 69.0. The 4-week run rate is 37.2% above this engagement's baseline. | not determinable from available data | Decide whether to continue delivery at negative margin or renegotiate the fee. Burn is inside the ceiling; the loss is on price, not hours. | engagement lead
20 | NEEDS REVIEW | Projected total is 6,328.8 hours against a 4,840-hour ceiling, projected_overrun_pct 30.8%, with burn at 56.2% and 228 days remaining. Run rate is 17.8% above baseline. Health band amber. | not determinable from available data | Review the delivery plan against the ceiling before the overrun is realised. Projection confidence is high. | engagement lead
25 | NEEDS REVIEW | Burn is 80.6%. Projection confidence is low: 2 of the trailing 4 readable weeks have no time logged against this engagement. Last entry 2026-08-07, 24 days ago. Top risk factor is reporting_gap. | not determinable from available data | Confirm the engagement's filing status before the projection is used. Reported with its confidence reason rather than acted on. | engagement lead
12 | NEEDS REVIEW | Person concentration is 85.4% across 2 people, with 24 days remaining to the 2026-09-24 end date. Burn is 67.5% and the health band is green. | not determinable from available data | Decide cover for the concentrated resource through to contract end. | engagement lead
19 | NEEDS REVIEW | Burn is 86.9% with 123.2 hours remaining and 40 days to run. Projected overrun is 5.1% and the run rate is 36.3% above baseline. Health score fell 12.2 to 76.6. | not determinable from available data | Review the remaining scope against 123.2 hours. | engagement lead
22 | NEEDS REVIEW | Projected overrun is 11.1% against a 1,520-hour ceiling with burn at 58.9%. Health band amber, score down 7.2 to 68.9. | not determinable from available data | Review the projection against the remaining 147 days. | engagement lead
15 | NEEDS REVIEW | Burn is 76.1% with 845.5 hours remaining and 46 days to run. Projected overrun is 0% and the run rate is 21.2% below baseline. | not determinable from available data | Monitor to contract end on 2026-10-16. No decision required this period. | engagement lead
2 | NEEDS REVIEW | The contract ended 2026-08-21 and the engagement is still status active. Burn is 29.1%, 1,404.1 hours remain against the ceiling, and wip_unbilled is -156,504.30 against invoiced 280,394.40. | not determinable from available data | Decide whether to close the engagement or extend the SOW, and resolve the negative unbilled position. Absent further time entries is not evidence of completion. | engagement lead

## Data Quality
Record quality — entries in the period
Time entries in the period | 2774 | entry_count
Filed after the period closed | 160 | late_entries
Filed late, as a percentage | 5.8 | late_entry_pct
No billable flag set | 2 | null_billable
Redundant rows: same person, engagement, day and hours | 1 | suspected_duplicates
Distinct duplicate groups | 1 | duplicate_groups
Reporting coverage by week
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE
Data notes
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this workbook, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
engagement_id | projection_confidence | confidence_reason
25 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement