## Summary
Delivery and margin review
Period | 2026-08
Run id | pack-check-seed-42
Scoring model version | v1.0
Portfolio
Engagements in the book
Examined in detail
Ceiling hours
Hours to date
Ceiling amount
Over their ceiling
Above 70% burn
Not in the green band
Above 70% person concentration
Projections reported low confidence
Exceptions raised
Reporting coverage
Weeks below the coverage floor | 1
Lowest weekly reporting coverage | 16.7

## Engagements
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | ceiling_amount | person_concentration_pct | people_count | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | examined | hours_remaining | weekly_run_rate_4wk | weeks_counted | weeks_with_no_hours | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | run_rate_vs_baseline_pct | days_since_last_entry | late_entry_pct | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 | 29.1 | 420591.6 | 55.5 | 3 | 99.7 | green | -0.3 | payment_behaviour | yes | 1404.1 | 17.55 | 4 | 0 | 575.9 | 0 | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | -32 | 0 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 | 83.2 | 86.8 | 29.5 | 29 | 1.7
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 | 68.3 | 232180 | 46.2 | 3 | 98.3 | green | -0.9 | burn_trajectory | no
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 | 65.1 | 133038.43 | 24.8 | 5 | 69 | amber | -11.2 | margin | yes | 938.5 | 68.88 | 4 | 0 | 2145.1 | 0 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 37.2 | 0 | 3.4 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 | -17.6 | 87 | 44 | 41.1 | 6.9
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 | 45.4 | 393680 | 45 | 3 | 100 | green | 31.2 |  | no
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1336.4 | 131 | 274176 | 48.9 | 4 | 53.5 | amber | -3.8 | burn_trajectory | yes | -316.4 | 32.15 | 4 | 0 | 2503 | 145.4 | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | -1.7 | 3 | 2.1 | 42180.92 | 42180.92 | 351264.68 | 206372.8 | 393445.6 | 24.7 | 90 | 24.3 | 25.3 | -4
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 | 124.5 | 241737.6 | 54.1 | 2 | 59.5 | amber | -5.5 | burn_trajectory | yes | -191.2 | 41.73 | 4 | 0 | 1394.4 | 78.8 | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 12.5 | 0 | 3.1 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 | 33.5 | 87 | 32.8 | 31.3 | 4.5
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 | 57.1 | 1332713.2 | 44.7 | 3 | 73.1 | green | -6.6 | burn_trajectory | no
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 998.4 | 67.5 | 478040 | 85.4 | 2 | 99.9 | green | 0.4 | payment_behaviour | yes | 481.6 | 34.03 | 4 | 0 | 1115.1 | 0 | high | 4 readable weeks with time logged in every one, 9.9% of entries filed after the period closed | 1.3 | 0 | 9.9 | 261087.5 | 207099.5 | 21938.5 | 138190.2 | 283026 | 51.2 | 88.7 | 39.8 | 39.7 | 0.4
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 | 65.5 | 812800 | 63.6 | 3 | 89.1 | green | -0.2 | burn_trajectory | no
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 | 76.1 | 1069080 | 50.2 | 4 | 94.4 | green | 10.2 | burn_trajectory | yes | 845.5 | 71.18 | 4 | 0 | 3162.2 | 0 | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | -21.2 | 0 | 6.5 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 | 50.7 | 88.8 | 36.7 | 35.5 | 3.4
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 | 32 | 1955100 | 41.7 | 3 | 100 | green | 0.2 |  | no
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 | 68.8 | 217906.8 | 53.2 | 3 | 94.1 | green | -5.7 | burn_trajectory | no
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 | 86.9 | 262260 | 59.5 | 2 | 76.6 | green | -12.2 | burn_trajectory | yes | 123.2 | 29.88 | 4 | 0 | 987.5 | 5.1 | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 36.3 | 0 | 7.5 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 | 51.6 | 86.4 | 29.7 | 30.8 | -3.7
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 | 56.2 | 1154243.2 | 33 | 6 | 64 | amber | 0.8 | burn_trajectory | yes | 2119.3 | 110.78 | 4 | 0 | 6328.8 | 30.8 | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 17.8 | 0 | 7.8 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 | 75 | 89.1 | 55 | 51.7 | 6.5
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 | 58.9 | 443840 | 33.1 | 4 | 68.9 | amber | -7.2 | burn_trajectory | yes | 624.8 | 37.78 | 4 | 0 | 1688.5 | 11.1 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 3.3 | 0 | 3.4 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 | 49.8 | 90.9 | 46.2 | 44.1 | 4.7
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 | 37.8 | 455731.2 | 55.7 | 2 | 99.3 | green | -0.7 | payment_behaviour | no
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 | 80.6 | 688080 | 53.7 | 3 | 76.6 | green | -9.4 | reporting_gap | yes | 472.2 | 22.53 | 4 | 2 | 2144.8 | 0 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | -46.6 | 24 | 0 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 | 50.2 | 87.4 | 39.8 | 39.7 | 0.4
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1108.6 | 56.6 | 482904.8 | 37.1 | 5 | 85.6 | green | -1.3 | burn_trajectory | no

## Time Detail
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | pct_active_reporting | firm_wide_gap
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11 | 100 | FALSE
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17 | 100 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24 | 94.1 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7 | 76.5 | FALSE
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37 | 100 | FALSE
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | 16.7 | TRUE
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51 | 94.4 | FALSE
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86 | 94.1 | FALSE
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17 | 76.5 | FALSE
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10 | 100 | FALSE
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22 | 94.4 | FALSE
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27 | 94.1 | FALSE
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4 | 76.5 | FALSE
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23 | 100 | FALSE
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49 | 94.4 | FALSE
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35 | 100 | FALSE
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19 | 94.4 | FALSE
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3 | 76.5 | FALSE
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52 | 100 | FALSE
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | 16.7 | TRUE
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67 | 94.4 | FALSE
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82 | 94.1 | FALSE
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12 | 76.5 | FALSE
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17 | 100 | FALSE
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16 | 94.4 | FALSE
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29 | 94.1 | FALSE
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9 | 76.5 | FALSE
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58 | 100 | FALSE
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60 | 94.4 | FALSE
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57 | 94.1 | FALSE
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10 | 76.5 | FALSE
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | 100 | FALSE
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | 94.4 | FALSE
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | 94.1 | FALSE
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | 76.5 | FALSE
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70 | 100 | FALSE
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66 | 94.4 | FALSE
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50 | 94.1 | FALSE
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15 | 76.5 | FALSE
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19 | 100 | FALSE
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57 | 94.4 | FALSE
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19 | 94.1 | FALSE
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4 | 76.5 | FALSE
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12 | 100 | FALSE
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3 | 94.4 | FALSE
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31 | 100 | FALSE
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27 | 94.4 | FALSE
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9 | 76.5 | FALSE
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84 | 100 | FALSE
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95 | 94.4 | FALSE
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99 | 94.1 | FALSE
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29 | 76.5 | FALSE
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48 | 100 | FALSE
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26 | 94.4 | FALSE
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39 | 94.1 | FALSE
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4 | 76.5 | FALSE
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13 | 100 | FALSE
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | 16.7 | TRUE
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16 | 94.4 | FALSE
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16 | 94.1 | FALSE
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46 | 94.4 | FALSE
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52 | 94.1 | FALSE
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18 | 76.5 | FALSE
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | 100 | FALSE
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | 94.4 | FALSE
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | 94.1 | FALSE
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | 76.5 | FALSE

## Exceptions
engagement_id | flag | situation | cause | recommended_action | decision_owner
No engagement was flagged by scope-escalation this period.

## Data Quality
Record quality — entries in the period
Time entries in the period | 2774 | entry_count
Filed after the period closed | 160 | late_entries
Filed late, as a percentage | 5.8 | late_entry_pct
No billable flag set | 2 | null_billable
Redundant rows: same person, engagement, day and hours | 1 | suspected_duplicates
Distinct duplicate groups | 1 | duplicate_groups
Reporting coverage by week
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE
Data notes
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this workbook, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
engagement_id | projection_confidence | confidence_reason
25 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement