## Summary
Delivery and Margin Review — 2026-08
Period 2026-08-01 to 2026-08-31 · as of 2026-08-31 · run_id delivery-review-2026-08 · scoring model v1.0
Every figure below is a value returned by a BizData tool call. Nothing on any tab is calculated in this workbook.
Portfolio
Measure | Value | Source field | Note
Active engagements in period | 18 | list_engagements.total_count | All 18 rows returned in one page; next_cursor was null.
Engagements examined in detail | 9 | step 4 trigger set | Burn over 70%, non-green band, or contract end date inside the period.
Time entries in period | 2774 | data_quality.entry_count
Late-filed entries | 160 | data_quality.late_entries
Late entry share | 5.8 | data_quality.late_entry_pct | Below the 20% threshold at which the period would be too unstable to review.
Weeks with a firm-wide reporting gap | 1 | data_completeness.weeks_with_gap | Week starting 2026-08-10. See Data Quality tab.
Lowest weekly reporting coverage | 16.7 | data_completeness.lowest_pct_active_reporting | A filing gap, not a change in delivery. Excluded from run rates by the tool.
Engagements flagged RED | 3 | Exceptions tab | Engagements 5, 8 and 9.
Engagements flagged NEEDS REVIEW | 6 | Exceptions tab
Read this first
Reporting coverage in the week starting 2026-08-10 was 16.7% of active engagements (3 of 18). Delivery for that week cannot be measured. It is a reporting gap, not a slowdown.
Three engagements need a partner decision this month: 5 (margin -17.6% on a fixed fee), 8 (burn 131%, projected overrun 145.4%) and 9 (burn 124.5%, projected overrun 78.8%).
Engagement 25's projection carries low confidence — 2 of the trailing 4 readable weeks have no time logged against it — and should not be acted on until the lead confirms status.
Burn and margin are measured independently and are not reconciled. Engagement 5 sits inside its hour ceiling at 65.1% burn while its cost has passed the fixed fee. Both are true.

## Engagements
Engagements — active portfolio at 2026-08-31
Columns to P come from list_engagements. Q to AM come from get_engagement_burn and get_financials and are populated only for the engagements examined at step 4; blank means not called, not zero.
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | ceiling_amount | hours_remaining | weekly_run_rate_4wk | baseline_weekly_run_rate | run_rate_vs_baseline_pct | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | person_concentration_pct | people_count | last_entry_date | days_since_last_entry | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct | examined | flag
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 | 29.1 | 99.7 | green | -0.3 | payment_behaviour | 420591.6 | 1404.1 | 17.55 | 25.83 | -32 | 575.9 | 0 | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | 55.5 | 3 | 2026-08-21 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 | 83.2 | 86.8 | 29.5 | 29 | 1.7 | yes | NEEDS REVIEW
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 | 68.3 | 98.3 | green | -0.9 | burn_trajectory | 232180 | [22 empty] | no
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 | 65.1 | 69 | amber | -11.2 | margin | 133038.43 | 938.5 | 68.88 | 50.2 | 37.2 | 2145.1 | 0 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 24.8 | 5 | 2026-08-31 | 0 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 | -17.6 | 87 | 44 | 41.1 | 6.9 | yes | RED
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 | 45.4 | 100 | green | 31.2 |  | 393680 | [22 empty] | no
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1336.4 | 131 | 53.5 | amber | -3.8 | burn_trajectory | 274176 | -316.4 | 32.15 | 32.71 | -1.7 | 2503 | 145.4 | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | 48.9 | 4 | 2026-08-28 | 3 | 42180.92 | 42180.92 | 351264.68 | 206372.8 | 393445.6 | 24.7 | 90 | 24.3 | 25.3 | -4 | yes | RED
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 | 124.5 | 59.5 | amber | -5.5 | burn_trajectory | 241737.6 | -191.2 | 41.73 | 37.08 | 12.5 | 1394.4 | 78.8 | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 54.1 | 2 | 2026-08-31 | 0 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 | 33.5 | 87 | 32.8 | 31.3 | 4.5 | yes | RED
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 | 57.1 | 73.1 | green | -6.6 | burn_trajectory | 1332713.2 | [22 empty] | no
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 998.4 | 67.5 | 99.9 | green | 0.4 | payment_behaviour | 478040 | [22 empty] | no
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 | 65.5 | 89.1 | green | -0.2 | burn_trajectory | 812800 | [22 empty] | no
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 | 76.1 | 94.4 | green | 10.2 | burn_trajectory | 1069080 | 845.5 | 71.18 | 90.36 | -21.2 | 3162.2 | 0 | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | 50.2 | 4 | 2026-08-31 | 0 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 | 50.7 | 88.8 | 36.7 | 35.5 | 3.4 | yes | NEEDS REVIEW
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 | 32 | 100 | green | 0.2 |  | 1955100 | [22 empty] | no
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 | 68.8 | 94.1 | green | -5.7 | burn_trajectory | 217906.8 | [22 empty] | no
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 | 86.9 | 76.6 | green | -12.2 | burn_trajectory | 262260 | 123.2 | 29.88 | 21.91 | 36.3 | 987.5 | 5.1 | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 59.5 | 2 | 2026-08-31 | 0 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 | 51.6 | 86.4 | 29.7 | 30.8 | -3.7 | yes | NEEDS REVIEW
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 | 56.2 | 64 | amber | 0.8 | burn_trajectory | 1154243.2 | 2119.3 | 110.78 | 94 | 17.8 | 6328.8 | 30.8 | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 33 | 6 | 2026-08-31 | 0 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 | 75 | 89.1 | 55 | 51.7 | 6.5 | yes | NEEDS REVIEW
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 | 58.9 | 68.9 | amber | -7.2 | burn_trajectory | 443840 | 624.8 | 37.78 | 36.56 | 3.3 | 1688.5 | 11.1 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 33.1 | 4 | 2026-08-31 | 0 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 | 49.8 | 90.9 | 46.2 | 44.1 | 4.7 | yes | NEEDS REVIEW
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 | 37.8 | 99.3 | green | -0.7 | payment_behaviour | 455731.2 | [22 empty] | no
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 | 80.6 | 76.6 | green | -9.4 | reporting_gap | 688080 | 472.2 | 22.53 | 42.2 | -46.6 | 2144.8 | 0 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | 53.7 | 3 | 2026-08-07 | 24 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 | 50.2 | 87.4 | 39.8 | 39.7 | 0.4 | yes | NEEDS REVIEW
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1108.6 | 56.6 | 85.6 | green | -1.3 | burn_trajectory | 482904.8 | [22 empty] | no

## Time Detail
Time Detail — get_time_summary(group_by='engagement,week'), 2026-08-01 to 2026-08-31
All 75 rows as returned, one call covering every engagement. Rows in the week starting 2026-08-10 are marked: that week's firm-wide coverage was 16.7%, so those rows record what was filed and not what was delivered. Do not average the weekly rows into a run rate — the tool's weekly_run_rate_4wk already excludes the gap week.
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | reporting coverage note
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | FIRM-WIDE REPORTING GAP week — incomplete filing, not a delivery change
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | FIRM-WIDE REPORTING GAP week — incomplete filing, not a delivery change
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | engagement not in the active portfolio list
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | engagement not in the active portfolio list
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | engagement not in the active portfolio list
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | engagement not in the active portfolio list
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | FIRM-WIDE REPORTING GAP week — incomplete filing, not a delivery change
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | engagement not in the active portfolio list
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | engagement not in the active portfolio list
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | engagement not in the active portfolio list
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | engagement not in the active portfolio list

## Exceptions
Exceptions — engagements requiring a decision
Classification was applied by judgement against the step 4 triggers of assemble-delivery-pack. The scope-escalation skill that normally decides RED vs NEEDS REVIEW is not present on this machine; see the Data Quality tab.
engagement_id | client_name | name | flag | situation | cause | recommended_action | decision_owner
5 | Pentland Media Group | Procurement Modernisation | RED | Margin -17.6% on a fixed fee. cost_to_date 156,515.8 exceeds ceiling_amount 133,038.43; billable_value_to_date 330,261.2, wip_unbilled 247,112.18, invoiced 83,149.02 of which 49,889.41 paid. Hours burn only 65.1%, so the hour ceiling does not show the loss. Health 69.0 amber, down 11.2 on the prior month; top risk factor margin. Run rate 68.88 hrs/wk is 37.2% above the 50.2 baseline, with 40 days remaining. | Not determinable from available data. Cost has passed the fixed fee while hours remain inside the hour ceiling, so the two ceilings disagree. | Stop-work or repricing decision this month. Every further hour is delivered below cost, and the run rate is rising, not falling. | partner
8 | Braemar Retail Corporation | Regulatory Reporting Programme | RED | Burn 131.0% of the 1,020-hour ceiling at 1,336.4 hours, hours_remaining -316.4, projected total 2,503.0 hours and projected overrun 145.4% on a high-confidence projection. Fixed fee: ceiling_amount 274,176 against billable_value_to_date 393,445.6, wip_unbilled 351,264.68, margin 24.7%. 254 days still to run. | Not determinable from available data. Run rate is 32.15 hrs/wk against a 32.71 baseline (-1.7%), so the overrun is not a recent acceleration. | Decide between a change order to lift the ceiling and a scope reduction for the remaining 254 days. Continuing unchanged commits roughly a further 1,167 projected hours against an already exhausted ceiling. | engagement lead, with partner sign-off on any change order
9 | Northfield Municipal Group | Pricing Modernisation | RED | Burn 124.5% of the 780-hour ceiling at 971.2 hours, hours_remaining -191.2, projected total 1,394.4 hours and projected overrun 78.8% on a high-confidence projection. Fixed fee: ceiling_amount 241,737.6 against billable_value_to_date 309,550, wip_unbilled 172,915.71, margin 33.5%. 71 days remaining, delivered by 2 people at 54.1% concentration. | Not determinable from available data. Run rate 41.73 hrs/wk is 12.5% above the 37.08 baseline. | Change order or scope cut before the remaining 71 days are worked. Two-person team also needs a continuity plan. | engagement lead, with partner sign-off on any change order
2 | Oakhaven Logistics Collective | Credit Risk Migration | NEEDS REVIEW | Contract end_date 2026-08-21 fell inside the period; days_remaining 0 and the burn call returns as_of 2026-08-21, yet status is still active. Final position: 575.9 of 1,980 ceiling hours, burn 29.1%, hours_remaining 1,404.1. Fixed fee fully invoiced and paid at 280,394.4 against billable_value_to_date 123,890.1, giving wip_unbilled -156,504.3 and margin 83.2%. Last entry 2026-08-21. | Not determinable from available data. The engagement was delivered in far fewer hours than the ceiling provided. | Close the engagement or record the extension. The negative unbilled position means the client has paid ahead of value delivered, which needs a stated answer before closeout. | engagement lead, with finance on the closeout position
15 | Ashcombe Health Partners | Workforce Planning Programme | NEEDS REVIEW | Burn 76.1% at 2,694.5 of 3,540 hours with 46 days remaining. Projected total 3,162.2 hours, projected overrun 0, high confidence. Run rate 71.18 hrs/wk is 21.2% below the 90.36 baseline. Margin 50.7%, realisation 88.8%. Health 94.4 green, up 10.2. Invoiced 453,254.3 of which 372,346 paid. | Not applicable: no adverse finding. Listed because burn exceeds 70%. | No decision needed. Projection lands inside the ceiling. | engagement lead (monitoring only)
19 | Thornbury Retail Partners | Grid Analytics Assessment | NEEDS REVIEW | Burn 86.9% at 816.8 of 940 hours, hours_remaining 123.2, projected overrun 5.1% high confidence, 40 days remaining. Run rate 29.88 hrs/wk is 36.3% above the 21.91 baseline. Health 76.6 green but down 12.2 on the prior month. Two people, 59.5% concentration. Margin 51.6%. | Not determinable from available data. | Time-and-materials, so the ceiling is the billing limit: confirm the client will authorise beyond 940 hours, or land the engagement inside it. | engagement lead
20 | Quarrymoor Transit Partners | Inventory Implementation | NEEDS REVIEW | Burn 56.2% but projected total 6,328.8 hours against a 4,840-hour ceiling, projected overrun 30.8% on a high-confidence projection, with 228 days remaining. Health 64.0 amber. Run rate 110.78 hrs/wk is 17.8% above the 94.0 baseline. Margin 75.0%; dso_days 55.0 against a client baseline of 51.7 (payment behaviour change 6.5%). | Not determinable from available data. Burn looks comfortable because the ceiling is large and the engagement is young relative to it. | Raise the ceiling or reset the plan now, while 228 days remain, rather than at the point of breach. | engagement lead
22 | Fernhollow Financial Trust | Billing Platform Assessment | NEEDS REVIEW | Health 68.9 amber, down 7.2 on the prior month. Burn 58.9%, projected total 1,688.5 against a 1,520-hour ceiling, projected overrun 11.1% high confidence, 147 days remaining. Invoiced 197,232.6 of which 110,441.3 paid; dso_days 46.2 against a 44.1 baseline. Margin 49.8%, realisation 90.9%. | Not determinable from available data. | Confirm the ceiling covers the plan for the remaining 147 days, and chase the 86,791.30 invoiced but unpaid. | engagement lead
25 | Stonebridge Energy Group | Billing Platform Implementation | NEEDS REVIEW | Burn 80.6% at 1,967.8 of 2,440 hours. projection_confidence low, reason: 2 of the trailing 4 readable weeks have no time logged against this engagement. Last entry 2026-08-07, 24 days before period end; 32 entries in the period against a baseline run rate of 42.2 hrs/wk. top_risk_factor reporting_gap. Margin 50.2%, realisation 87.4%, 55 days remaining. | Not determinable from available data. Absent time entries do not establish whether delivery stopped or filing did. | Confirm with the engagement lead whether work is ongoing before the projection is used for anything. The projected total of 2,144.8 hours carries low confidence and should not be acted on as it stands. | engagement lead

## Data Quality
Data Quality
Weekly reporting coverage — data_completeness.weeks
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap | note
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE | Reporting coverage was 16.7% in the week of 2026-08-10 (3 of 18 active engagements filed). Delivery for that week cannot be measured. This is a filing artifact, not a delivery slowdown, and the tool already excludes it from every run rate and projection.
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE | Week extends past the period end at 2026-09-06; only 2026-08-31 falls inside the period, so lower coverage here is expected.
Entry quality — data_quality
field | value |  |  |  |  | note
entry_count | 2774
late_entries | 160
late_entry_pct | 5.8 |  |  |  |  | Below 20%, so the period is stable enough to review.
null_billable | 2 |  |  |  |  | 2 entries with no billable flag.
suspected_duplicates | 1 |  |  |  |  | 1 suspected duplicate in 1 duplicate group.
duplicate_groups | 1
Low-confidence projections
engagement_id | projection_confidence | projected_total_hours | projected_overrun_pct |  |  | confidence_reason
25 | low | 2144.8 | 0 |  |  | 2 of the trailing 4 readable weeks have no time logged against this engagement
Run notes and limits of this pack
The scope-escalation skill referenced at step 6 of assemble-delivery-pack is not present on this machine. RED / NEEDS REVIEW classifications on the Exceptions tab were applied by judgement against the triggers in step 4, not by that skill's rules, and should be re-run once it is available.
The bundled scripts/build_workbook.py referenced by assemble-delivery-pack is not present either. This workbook was produced by a substitute builder that transcribes tool values only and computes nothing.
person_concentration_pct is returned by get_engagement_burn but not by list_engagements, so the step 4 trigger for concentration above 70% could only be evaluated for the 9 engagements examined. None of those 9 exceeded 70% (highest: 59.5% on engagement 19). Concentration is not determinable for the other 9 engagements without a burn call for each.
get_time_summary returned time in the period for engagement_id 14 (Asset Register Programme) and engagement_id 30 (Asset Register Migration). Neither appears in list_engagements(status=active), whose total_count was 18. Their rows are carried on the Time Detail tab as returned but they are outside the active portfolio and receive no summary line on the Engagements tab.
data_quality for the period: 2,774 entries, 160 late (late_entry_pct 5.8, below the 20% stop threshold), 2 null_billable, 1 suspected_duplicate in 1 duplicate group.
Figures no tool returned, therefore left out rather than derived: portfolio-level totals for burn, margin, realisation or coverage. The tools return these per engagement only, and a portfolio percentage worked out here could disagree with the database.