## Summary
Delivery and Margin Review
Period 2026-08 ¦ as of 2026-08-31 ¦ run_id delivery-review-2026-08
Every figure in this workbook was returned by a bizdataConnector tool call. Nothing here was calculated during assembly.
Portfolio
Active engagements returned | 18 of 18 (total_count matched, no further pages)
Period covered | 2026-08-01 to 2026-08-31
Time rows returned | 75 of 75, truncated: False
Engagements examined in detail | 10 — ids 2, 5, 8, 9, 12, 15, 19, 20, 22, 25
Reporting coverage
Weeks with a firm-wide reporting gap | 1
Lowest weekly coverage | 16.7% of active engagements reporting
Gap week: 2026-08-10 to 2026-08-16 | 16.7% reporting (3 of 18). Filing artifact — delivery for this week cannot be measured. Already excluded from run rates and projections.
Late entries in period | 160 of 2774 (5.8%) — below the 20% stop threshold
Trigger lists (all four written out)
A burn_pct > 70 | 8 Regulatory Reporting Programme, 9 Pricing Modernisation, 15 Workforce Planning Programme, 19 Grid Analytics Assessment, 25 Billing Platform Implementation
B health_band not green | 5 Procurement Modernisation, 8 Regulatory Reporting Programme, 9 Pricing Modernisation, 20 Inventory Implementation, 22 Billing Platform Assessment
C person_concentration_pct > 70 | 12 Credit Risk Programme
D end_date on or before period end | 2 Credit Risk Migration
Exceptions raised
RED | 3 — 8 Regulatory Reporting Programme, 9 Pricing Modernisation, 5 Procurement Modernisation
NEEDS REVIEW | 7 — 12 Credit Risk Programme, 25 Billing Platform Implementation, 20 Inventory Implementation, 19 Grid Analytics Assessment, 22 Billing Platform Assessment, 2 Credit Risk Migration, 15 Workforce Planning Programme

## Engagements
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | ceiling_amount | hours_remaining | weekly_run_rate_4wk | run_rate_vs_baseline_pct | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | person_concentration_pct | people_count | last_entry_date | days_since_last_entry | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct | examined | flag
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 | 29.1 | 99.7 | green | -0.3 | payment_behaviour | 420591.6 | 1404.1 | 17.55 | -32 | 575.9 | 0 | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | 55.5 | 3 | 2026-08-21 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 | 83.2 | 86.8 | 29.5 | 29 | 1.7 | yes | NEEDS REVIEW
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 | 68.3 | 98.3 | green | -0.9 | burn_trajectory | 232180 |  | 19.13 |  | 808.8 | 0 | low | 13.6% of the period's entries were filed after the period closed | 46.2 | 3 | [12 empty] | screened (concentration only)
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 | 65.1 | 69 | amber | -11.2 | margin | 133038.43 | 938.5 | 68.88 | 37.2 | 2145.1 | 0 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 24.8 | 5 | 2026-08-31 | 0 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 | -17.6 | 87 | 44 | 41.1 | 6.9 | yes | RED
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 | 45.4 | 100 | green | 31.2 |  | 393680 |  | 20.6 |  | 1202.2 | 0 | high | 4 readable weeks with time logged in every one, 7.9% of entries filed after the period closed | 45 | 3 | [12 empty] | screened (concentration only)
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1336.4 | 131 | 53.5 | amber | -3.8 | burn_trajectory | 274176 | -316.4 | 32.15 | -1.7 | 2503 | 145.4 | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | 48.9 | 4 | 2026-08-28 | 3 | 42180.92 | 42180.92 | 351264.68 | 206372.8 | 393445.6 | 24.7 | 90 | 24.3 | 25.3 | -4 | yes | RED
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 | 124.5 | 59.5 | amber | -5.5 | burn_trajectory | 241737.6 | -191.2 | 41.73 | 12.5 | 1394.4 | 78.8 | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 54.1 | 2 | 2026-08-31 | 0 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 | 33.5 | 87 | 32.8 | 31.3 | 4.5 | yes | RED
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 | 57.1 | 73.1 | green | -6.6 | burn_trajectory | 1332713.2 |  | 70.43 |  | 5275.8 | 6.8 | high | 4 readable weeks with time logged in every one, 2.2% of entries filed after the period closed | 44.7 | 3 | [12 empty] | screened (concentration only)
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 998.4 | 67.5 | 99.9 | green | 0.4 | payment_behaviour | 478040 | 481.6 | 34.03 | 1.3 | 1115.1 | 0 | high | 4 readable weeks with time logged in every one, 9.9% of entries filed after the period closed | 85.4 | 2 | 2026-08-31 | 0 | 261087.5 | 207099.5 | 21938.5 | 138190.2 | 283026 | 51.2 | 88.7 | 39.8 | 39.7 | 0.4 | yes | NEEDS REVIEW
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 | 65.5 | 89.1 | green | -0.2 | burn_trajectory | 812800 |  | 64.13 |  | 3004.4 | 0 | high | 4 readable weeks with time logged in every one, 4.3% of entries filed after the period closed | 63.6 | 3 | [12 empty] | screened (concentration only)
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 | 76.1 | 94.4 | green | 10.2 | burn_trajectory | 1069080 | 845.5 | 71.18 | -21.2 | 3162.2 | 0 | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | 50.2 | 4 | 2026-08-31 | 0 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 | 50.7 | 88.8 | 36.7 | 35.5 | 3.4 | yes | NEEDS REVIEW
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 | 32 | 100 | green | 0.2 |  | 1955100 |  | 34.55 |  | 3489.9 | 0 | high | 4 readable weeks with time logged in every one, 4.0% of entries filed after the period closed | 41.7 | 3 | [12 empty] | screened (concentration only)
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 | 68.8 | 94.1 | green | -5.7 | burn_trajectory | 217906.8 |  | 12.83 |  | 738.6 | 0 | high | 4 readable weeks with time logged in every one, 2.2% of entries filed after the period closed | 53.2 | 3 | [12 empty] | screened (concentration only)
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 | 86.9 | 76.6 | green | -12.2 | burn_trajectory | 262260 | 123.2 | 29.88 | 36.3 | 987.5 | 5.1 | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 59.5 | 2 | 2026-08-31 | 0 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 | 51.6 | 86.4 | 29.7 | 30.8 | -3.7 | yes | NEEDS REVIEW
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 | 56.2 | 64 | amber | 0.8 | burn_trajectory | 1154243.2 | 2119.3 | 110.78 | 17.8 | 6328.8 | 30.8 | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 33 | 6 | 2026-08-31 | 0 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 | 75 | 89.1 | 55 | 51.7 | 6.5 | yes | NEEDS REVIEW
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 | 58.9 | 68.9 | amber | -7.2 | burn_trajectory | 443840 | 624.8 | 37.78 | 3.3 | 1688.5 | 11.1 | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 33.1 | 4 | 2026-08-31 | 0 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 | 49.8 | 90.9 | 46.2 | 44.1 | 4.7 | yes | NEEDS REVIEW
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 | 37.8 | 99.3 | green | -0.7 | payment_behaviour | 455731.2 |  | 17.43 |  | 1026.5 | 0 | high | 4 readable weeks with time logged in every one, 4.4% of entries filed after the period closed | 55.7 | 2 | [12 empty] | screened (concentration only)
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 | 80.6 | 76.6 | green | -9.4 | reporting_gap | 688080 | 472.2 | 22.53 | -46.6 | 2144.8 | 0 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | 53.7 | 3 | 2026-08-07 | 24 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 | 50.2 | 87.4 | 39.8 | 39.7 | 0.4 | yes | NEEDS REVIEW
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1108.6 | 56.6 | 85.6 | green | -1.3 | burn_trajectory | 482904.8 |  | 47.83 |  | 1908 | 0 | low | 20.9% of the period's entries were filed after the period closed | 37.1 | 5 | [12 empty] | screened (concentration only)
Blank cells mean the tool was not called for that engagement, not that the value is zero. Columns R to AB for engagements marked 'screened' come from a concentration-screening get_engagement_burn call; get_financials was not called for them.

## Time Detail
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | week coverage | note
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11 | 100%
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22 | 94.4%
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17 | 100%
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11 | 94.4%
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24 | 94.1%
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7 | 76.5%
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37 | 100%
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | 16.7% | Firm-wide reporting gap. Filing artifact — this week's figures are incomplete and delivery for it cannot be measured. Excluded from run rates and projections; do not average these rows to re-derive a run rate.
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51 | 94.4%
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86 | 94.1%
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17 | 76.5%
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10 | 100%
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22 | 94.4%
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27 | 94.1%
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4 | 76.5%
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23 | 100%
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49 | 94.4%
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22 | 94.1%
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35 | 100%
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19 | 94.4%
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40 | 94.1%
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3 | 76.5%
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52 | 100%
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | 16.7% | Firm-wide reporting gap. Filing artifact — this week's figures are incomplete and delivery for it cannot be measured. Excluded from run rates and projections; do not average these rows to re-derive a run rate.
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67 | 94.4%
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82 | 94.1%
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12 | 76.5%
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17 | 100%
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16 | 94.4%
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29 | 94.1%
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9 | 76.5%
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58 | 100%
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60 | 94.4%
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57 | 94.1%
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10 | 76.5%
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | 100%
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | 94.4%
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | 94.1%
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | 76.5%
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70 | 100%
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66 | 94.4%
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50 | 94.1%
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15 | 76.5%
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19 | 100%
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57 | 94.4%
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19 | 94.1%
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4 | 76.5%
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12 | 100%
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3 | 94.4%
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31 | 94.1%
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31 | 100%
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27 | 94.4%
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39 | 94.1%
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9 | 76.5%
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84 | 100%
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95 | 94.4%
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99 | 94.1%
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29 | 76.5%
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48 | 100%
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26 | 94.4%
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39 | 94.1%
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4 | 76.5%
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13 | 100%
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | 16.7% | Firm-wide reporting gap. Filing artifact — this week's figures are incomplete and delivery for it cannot be measured. Excluded from run rates and projections; do not average these rows to re-derive a run rate.
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16 | 94.4%
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16 | 94.1%
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32 | 100%
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23 | 100%
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46 | 94.4%
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52 | 94.1%
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18 | 76.5%
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | 100%
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | 94.4%
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | 94.1%
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | 76.5%

## Exceptions
engagement_id | flag | engagement | client | situation | cause | recommended_action | decision_owner
8 | RED | Regulatory Reporting Programme | Braemar Retail Corporation | Burn 131.0% with hours_remaining -316.4 against a 1020-hour ceiling; projected_total_hours 2503.0 and projected_overrun_pct 145.4 (projection_confidence high). 254 days remain on the contract. Fixed fee, ceiling_amount 274176.00, wip_unbilled 351264.68 against invoiced 42180.92. | not determinable from available data | Decide whether to raise a change order against SOW-2025-008 or halt work at the ceiling. Unbilled WIP of 351264.68 exceeds the fee ceiling and needs a billing decision alongside the scope decision. | engagement lead
9 | RED | Pricing Modernisation | Northfield Municipal Group | Burn 124.5% with hours_remaining -191.2 against a 780-hour ceiling; projected_total_hours 1394.4 and projected_overrun_pct 78.8 (projection_confidence high). 71 days remain. Fixed fee; wip_unbilled 172915.71, margin_pct 33.5. | not determinable from available data | Change order or scope reduction decision before the remaining 71 days are worked. Delivery is 2 people at 54.1% concentration. | engagement lead
5 | RED | Procurement Modernisation | Pentland Media Group | margin_pct -17.6 on a fixed-fee engagement: cost_to_date 156515.80 against ceiling_amount 133038.43, with billable_value_to_date 330261.20. health_band amber, health_score 69.0, down 11.2 on the prior period, top_risk_factor margin. Burn 65.1% with 40 days remaining and run rate 37.2% above this engagement's baseline. | not determinable from available data | Margin decision required: the engagement is loss-making at the current ceiling and the run rate is accelerating with 40 days to run. Confirm whether the fixed fee is renegotiable or delivery must be capped. | engagement lead
12 | NEEDS REVIEW | Credit Risk Programme | Stonebridge Energy Group | person_concentration_pct 85.4 across 2 people, with 24 days remaining to the 2026-09-24 end date. Burn 67.5%, health_band green, health_score 99.9, margin_pct 51.2 — no burn or health signal flags this engagement. | not determinable from available data | Key-person risk decision: confirm cover for the closing 24 days of the engagement. Flagged on concentration alone; it is invisible to burn and health screening. | engagement lead
25 | NEEDS REVIEW | Billing Platform Implementation | Stonebridge Energy Group | Burn 80.6% with 472.2 hours remaining and 55 days to run. projected_overrun_pct 0 but projection_confidence is low: 2 of the trailing 4 readable weeks have no time logged against this engagement. last_entry_date 2026-08-07, 24 days since last entry. top_risk_factor reporting_gap. | not determinable from available data — absent time entries are absent data and do not establish that delivery has stopped or completed | Confirm the filing position for this engagement before the projection is used for any commitment. The low-confidence projection is reported with its reason and should not be acted on. | engagement lead
20 | NEEDS REVIEW | Inventory Implementation | Quarrymoor Transit Partners | projected_overrun_pct 30.8 against a 4840-hour ceiling (projected_total_hours 6328.8, projection_confidence high) while burn is only 56.2%. health_band amber, health_score 64.0. Run rate 110.78 hours/week, 17.8% above this engagement's baseline. dso_days 55.0 against a 51.7-day baseline for this client. | not determinable from available data | Trajectory decision with 228 days still to run: the overrun is projected, not yet incurred, and is the cheapest point at which to act. | engagement lead
19 | NEEDS REVIEW | Grid Analytics Assessment | Thornbury Retail Partners | Burn 86.9% with 123.2 hours remaining and 40 days to run; projected_overrun_pct 5.1 (projection_confidence high). Run rate 36.3% above this engagement's baseline. health_band green but health_score down 12.2 on the prior period. Delivery is 2 people at 59.5% concentration. | not determinable from available data | Confirm the remaining 123.2 hours cover the scope to 2026-10-10, or raise the ceiling now. | engagement lead
22 | NEEDS REVIEW | Billing Platform Assessment | Fernhollow Financial Trust | health_band amber, health_score 68.9, down 7.2 on the prior period. Burn 58.9% with projected_overrun_pct 11.1 (projection_confidence high) and 147 days to run. margin_pct 49.8. paid 110441.30 against invoiced 197232.60, dso_days 46.2 versus a 44.1-day baseline for this client. | not determinable from available data | Review the amber band and the projected 11.1% overrun while 147 days remain. | engagement lead
2 | NEEDS REVIEW | Credit Risk Migration | Oakhaven Logistics Collective | end_date 2026-08-21 has passed and days_remaining is 0, but status is still active. Burn 29.1% against a 1980-hour ceiling; invoiced and paid 280394.40 against a ceiling_amount of 420591.60; wip_unbilled -156504.30. last_entry_date 2026-08-21. | not determinable from available data | Closure decision: confirm whether the engagement is complete and should be closed, or extended. Negative unbilled WIP of -156504.30 needs a billing reconciliation either way. | engagement lead
15 | NEEDS REVIEW | Workforce Planning Programme | Ashcombe Health Partners | Burn 76.1% with 845.5 hours remaining and 46 days to run. projected_total_hours 3162.2 against a 3540-hour ceiling, projected_overrun_pct 0 (projection_confidence high). Run rate 21.2% below this engagement's baseline. health_band green, health_score 94.4, up 10.2 on the prior period. | not determinable from available data | Monitor only. Flagged by the burn trigger; the projection does not show an overrun and no decision is required this period. | engagement lead

## Data Quality
Data Quality and Method Notes
Weekly reporting coverage
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE
Entry-level data quality
entry_count | late_entries | late_entry_pct | null_billable | suspected_duplicates | duplicate_groups
2774 | 160 | 5.8 | 2 | 1 | 1
Notes
Note 1 | REPORTING GAP — week of 2026-08-10 (2026-08-10 to 2026-08-16): pct_active_reporting 16.7%, 3 of 18 active engagements reporting, firm_wide_gap true. This is a filing artifact, not a change in delivery. Delivery for that week cannot be measured. The week is already excluded from weekly_run_rate_4wk, projected_total_hours and projected_overrun_pct, which are computed in SQL over readable weeks only. The engagement,week rows on the Time Detail tab include the week because they are a record of what was filed; they must not be averaged to re-derive a run rate.
Note 2 | Firm-wide data quality for the period: 2774 entries, 160 late (late_entry_pct 5.8), 2 null_billable, 1 suspected duplicate in 1 duplicate group. late_entry_pct is below the 20% stop threshold, so the period is stable enough to review.
Note 3 | Low projection confidence — engagement 25 Billing Platform Implementation: 2 of the trailing 4 readable weeks have no time logged against this engagement. The projection is reported with this reason attached and is not acted on.
Note 4 | Low projection confidence — engagement 29 Grid Analytics Integration: 20.9% of the period's entries were filed after the period closed. Not in the examined set (green band, burn 56.6%, concentration 37.1%, end date 2026-12-26); recorded here because the projection for it is labelled low confidence.
Note 5 | Low projection confidence — engagement 3 Revenue Assurance Optimisation: 13.6% of the period's entries were filed after the period closed. Not in the examined set (green band, burn 68.3%, concentration 46.2%); recorded here because the projection for it is labelled low confidence.
Note 6 | METHOD DEVIATION — trigger C screening. The skill specifies that person_concentration_pct is on every list_engagements row so that trigger C needs no tool call. That field is not present in the list_engagements response for this period; it is returned only by get_engagement_burn. To avoid skipping trigger C, get_engagement_burn was called for the eight active engagements not already in the A/B/D union (3, 7, 11, 13, 16, 18, 23, 29) for screening purposes. This surfaced engagement 12 at 85.4% concentration, which no other trigger would have caught. Screening figures for those eight are held in burn_screening_only in the source data; get_financials was not called for them.
Note 7 | METHOD DEVIATION — workbook build. The skill's bundled scripts/build_workbook.py is not present in the synced skill bundle (SKILL.md is the only file). An equivalent layout-only script was written for this run. It performs no calculation: every value it writes is read directly from the tool responses stored in pack.json.
Note 8 | METHOD DEVIATION — escalation criteria. The skill defers RED / NEEDS REVIEW assignment to a scope-escalation skill, which is not available in this session. Flags were assigned on stated criteria: RED where a ceiling is already breached with contract time remaining, or where margin_pct is negative; NEEDS REVIEW where an overrun is projected but not yet incurred, where concentration or contract status raises a question burn does not express, or where a projection is low confidence. Every figure supporting a flag is quoted from a tool response and can be re-read on the Engagements tab.
Note 9 | SCOPE — engagements 14 (Asset Register Programme) and 30 (Asset Register Migration) have time entries in the period but are not in the active engagement list for 2026-08-31. Their time rows are retained on the Time Detail tab as returned. They were not examined: the portfolio for this review is the 18 active engagements returned by list_engagements.
Note 10 | The engagements_active count in data_completeness falls from 18 to 17 for the weeks beginning 2026-08-24 and 2026-08-31, consistent with engagement 2 reaching its 2026-08-21 end date. Neither of those weeks is flagged firm_wide_gap.