## Slide 1
Delivery and margin review
2026-08 · 18 active engagements · 11 clients
Generated 2026-08-24
Scoring model v1.0
Run delivery-review-2026-08

## Slide 2
Portfolio summary
2026-08, active engagements, measured across the whole book
 | This period | Movement vs prior month
Active engagements | 18 | +0
Hours to date | 25,882.1 | +2,737.7
Ceiling hours | 44,390.0 | 
Portfolio burn | 58.3% | 
Revenue to date | 8,081,944 | 
Cost to date | 3,169,259 | 
Blended margin | 60.8% | -2.9pp
Mean health score | 83.4 | -1.2
In the green band | 13 of 18 | 
Blended margin is revenue less cost across the book, divided once. Fixed-price engagements take the fee as revenue; time and materials takes billable value at rate card.

## Slide 3
Margin by client
Blended across each client's active engagements, in percent
Chart: 
| Ashcombe Health Partners | Braemar Retail Corporation | Fernhollow Financial Trust | Lowmarsh Retail Partners | Merrivale Maritime Corporation | Northfield Municipal Group | Oakhaven Logistics Collective | Pentland Media Group | Quarrymoor Transit Partners | Stonebridge Energy Group | Thornbury Retail Partners
Margin % | 51 | 43.6 | 67.4 | 76.8 | 75.2 | 33.5 | 83.2 | -17.6 | 75 | 50.6 | 58.3
Lowest is Pentland Media Group at -17.6% across 1 engagement(s).

## Slide 4
Engagements at risk
8 of 10 engagements examined in detail, of 18 active
Engagement | Client | Burn | Margin | Health | Concentration | Ends
8 Regulatory Reporting Programme | Braemar Retail Corporation | 131.0% | 24.7% | 53.5 amber | 48.9% | 2027-05-12
9 Pricing Modernisation | Northfield Municipal Group | 124.5% | 33.5% | 59.5 amber | 54.1% | 2026-11-10
20 Inventory Implementation | Quarrymoor Transit Partners | 56.2% | 75.0% | 64.0 amber | 33.0% | 2027-04-16
22 Billing Platform Assessment | Fernhollow Financial Trust | 58.9% | 49.8% | 68.9 amber | 33.1% | 2027-01-25
5 Procurement Modernisation | Pentland Media Group | 65.1% | -17.6% | 69.0 amber | 24.8% | 2026-10-10
19 Grid Analytics Assessment | Thornbury Retail Partners | 86.9% | 51.6% | 76.6 green | 59.5% | 2026-10-10
25 Billing Platform Implementation | Stonebridge Energy Group | 80.6% | 50.2% | 76.6 green | 53.7% | 2026-10-25
15 Workforce Planning Programme | Ashcombe Health Partners | 76.1% | 50.7% | 94.4 green | 50.2% | 2026-10-16
Burn above 70% is amber and above 90% is red, the same thresholds the workbook applies. Ceilings are never re-baselined, so burn above 100% stays above 100%.

## Slide 5
RED · Regulatory Reporting Programme
Engagement 8 · Braemar Retail Corporation · fixed
Situation
Projected overrun is 145.4% against a ceiling of 1,020.0 hours, at high projection confidence. Burn is 131.0% of a 1,020.0 hour ceiling with 254 of 542 contract days remaining.
Burn | 131.0% | Margin | 24.7%
Hours to date | 1,336.4 | Ceiling hours | 1,020.0
Hours remaining | -316.4 | Projected overrun | 145.4%
Health | 53.5 | Band | amber
Cause
not determinable from available data
Recommended action
Hours are 316.4 past the 1,020.0 hour ceiling with 254 contract days remaining. Decide whether to stop work at the ceiling or raise a change order for the remaining scope, and confirm the client position on the hours already delivered past it. Engagement lead to decide.
Decision owner: engagement lead

## Slide 6
RED · Pricing Modernisation
Engagement 9 · Northfield Municipal Group · fixed
Situation
Projected overrun is 78.8% against a ceiling of 780.0 hours, at high projection confidence. Burn is 124.5% of a 780.0 hour ceiling with 71 of 291 contract days remaining.
Burn | 124.5% | Margin | 33.5%
Hours to date | 971.2 | Ceiling hours | 780.0
Hours remaining | -191.2 | Projected overrun | 78.8%
Health | 59.5 | Band | amber
Cause
not determinable from available data
Recommended action
Hours are 191.2 past the 780.0 hour ceiling with 71 contract days remaining. Decide whether to raise a change order or close out at the ceiling. Engagement lead to decide.
Decision owner: engagement lead

## Slide 7
RED · Inventory Implementation
Engagement 20 · Quarrymoor Transit Partners · fixed
Situation
Projected overrun is 30.8% against a ceiling of 4,840.0 hours, at high projection confidence.
Burn | 56.2% | Margin | 75.0%
Hours to date | 2,720.7 | Ceiling hours | 4,840.0
Hours remaining | 2,119.3 | Projected overrun | 30.8%
Health | 64.0 | Band | amber
Cause
not determinable from available data
Recommended action
Projection at the current run rate exceeds the 4,840.0 hour ceiling by 30.8% with 228 contract days remaining. Decide whether the run rate is reduced, the scope trimmed, or a change order raised now rather than at the ceiling. Engagement lead to decide.
Decision owner: engagement lead

## Slide 8
Data quality and caveats
2026-08, across the whole firm
Record quality | Count
Time entries in the period | 2,774
Filed after the period closed | 160 (5.8%)
No billable flag set | 2
Redundant rows: same person, engagement, day and hours | 1
Reporting coverage
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this pack, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
Engagement 25: 2 of the trailing 4 readable weeks have no time logged against this engagement
Figures come from the BizData tools and are reproduced in engagement-book-2026-08.xlsx. Scoring model v1.0.