## Summary
Delivery and margin review
Period | 2026-08
Run id | delivery-review-2026-08
Scoring model version | v1.0
Portfolio
Engagements in the book
Examined in detail
Ceiling hours
Hours to date
Ceiling amount
Over their ceiling
Above 70% burn
Not in the green band
Above 70% person concentration
Projections reported low confidence
Exceptions raised
Portfolio, as the tools measured it
Active engagements | 18
Clients | 11
In the green band | 13
Ceiling hours | 44390
Hours to date | 25882.1
Portfolio burn | 58.3
Revenue to date | 8081943.63
Cost to date | 3169258.7
Blended margin | 60.8
Mean health score | 83.4
Blended margin, movement vs prior month | -2.9
Mean health score, movement vs prior month | -1.2
Hours to date, movement vs prior month | 2737.7
Reporting coverage
Weeks below the coverage floor | 1
Lowest weekly reporting coverage | 16.7

## Engagements
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | ceiling_amount | person_concentration_pct | people_count | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | examined | hours_remaining | weekly_run_rate_4wk | weeks_counted | weeks_with_no_hours | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | run_rate_vs_baseline_pct | days_since_last_entry | late_entry_pct | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 |  | 420591.6 | 55.5 | 3 | 99.7 | green | -0.3 | payment_behaviour | yes | 1404.1 | 17.55 | 4 | 0 | 575.9 |  | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | -32 | 0 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 |  | 86.8 | 29.5 | 29 | 1.7
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 |  | 232180 | 46.2 | 3 | 98.3 | green | -0.9 | burn_trajectory | no
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 |  | 133038.43 | 24.8 | 5 | 69 | amber | -11.2 | margin | yes | 938.5 | 68.88 | 4 | 0 | 2145.1 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 37.2 | 0 | 3.4 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 |  | 87 | 44 | 41.1 | 6.9
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 |  | 393680 | 45 | 3 | 100 | green | 31.2 |  | no
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1336.4 |  | 274176 | 48.9 | 4 | 53.5 | amber | -3.8 | burn_trajectory | yes | -316.4 | 32.15 | 4 | 0 | 2503 |  | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | -1.7 | 3 | 2.1 | 42180.92 | 42180.92 | 351264.68 | 206372.8 | 393445.6 |  | 90 | 24.3 | 25.3 | -4
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 |  | 241737.6 | 54.1 | 2 | 59.5 | amber | -5.5 | burn_trajectory | yes | -191.2 | 41.73 | 4 | 0 | 1394.4 |  | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 12.5 | 0 | 3.1 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 |  | 87 | 32.8 | 31.3 | 4.5
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 |  | 1332713.2 | 44.7 | 3 | 73.1 | green | -6.6 | burn_trajectory | no
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 998.4 |  | 478040 | 85.4 | 2 | 99.9 | green | 0.4 | payment_behaviour | yes | 481.6 | 34.03 | 4 | 0 | 1115.1 |  | high | 4 readable weeks with time logged in every one, 9.9% of entries filed after the period closed | 1.3 | 0 | 9.9 | 261087.5 | 207099.5 | 21938.5 | 138190.2 | 283026 |  | 88.7 | 39.8 | 39.7 | 0.4
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 |  | 812800 | 63.6 | 3 | 89.1 | green | -0.2 | burn_trajectory | no
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 |  | 1069080 | 50.2 | 4 | 94.4 | green | 10.2 | burn_trajectory | yes | 845.5 | 71.18 | 4 | 0 | 3162.2 |  | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | -21.2 | 0 | 6.5 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 |  | 88.8 | 36.7 | 35.5 | 3.4
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 |  | 1955100 | 41.7 | 3 | 100 | green | 0.2 |  | no
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 |  | 217906.8 | 53.2 | 3 | 94.1 | green | -5.7 | burn_trajectory | no
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 |  | 262260 | 59.5 | 2 | 76.6 | green | -12.2 | burn_trajectory | yes | 123.2 | 29.88 | 4 | 0 | 987.5 |  | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 36.3 | 0 | 7.5 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 |  | 86.4 | 29.7 | 30.8 | -3.7
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 |  | 1154243.2 | 33 | 6 | 64 | amber | 0.8 | burn_trajectory | yes | 2119.3 | 110.78 | 4 | 0 | 6328.8 |  | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 17.8 | 0 | 7.8 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 |  | 89.1 | 55 | 51.7 | 6.5
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 |  | 443840 | 33.1 | 4 | 68.9 | amber | -7.2 | burn_trajectory | yes | 624.8 | 37.78 | 4 | 0 | 1688.5 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 3.3 | 0 | 3.4 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 |  | 90.9 | 46.2 | 44.1 | 4.7
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 |  | 455731.2 | 55.7 | 2 | 99.3 | green | -0.7 | payment_behaviour | no
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 |  | 688080 | 53.7 | 3 | 76.6 | green | -9.4 | reporting_gap | yes | 472.2 | 22.53 | 4 | 2 | 2144.8 |  | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | -46.6 | 24 | 0 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 |  | 87.4 | 39.8 | 39.7 | 0.4
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1108.6 |  | 482904.8 | 37.1 | 5 | 85.6 | green | -1.3 | burn_trajectory | no

## Time Detail
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | pct_active_reporting | firm_wide_gap
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11 | 100 | FALSE
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17 | 100 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24 | 94.1 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7 | 76.5 | FALSE
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37 | 100 | FALSE
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | 16.7 | TRUE
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51 | 94.4 | FALSE
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86 | 94.1 | FALSE
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17 | 76.5 | FALSE
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10 | 100 | FALSE
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22 | 94.4 | FALSE
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27 | 94.1 | FALSE
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4 | 76.5 | FALSE
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23 | 100 | FALSE
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49 | 94.4 | FALSE
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35 | 100 | FALSE
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19 | 94.4 | FALSE
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3 | 76.5 | FALSE
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52 | 100 | FALSE
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | 16.7 | TRUE
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67 | 94.4 | FALSE
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82 | 94.1 | FALSE
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12 | 76.5 | FALSE
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17 | 100 | FALSE
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16 | 94.4 | FALSE
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29 | 94.1 | FALSE
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9 | 76.5 | FALSE
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58 | 100 | FALSE
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60 | 94.4 | FALSE
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57 | 94.1 | FALSE
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10 | 76.5 | FALSE
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | 100 | FALSE
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | 94.4 | FALSE
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | 94.1 | FALSE
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | 76.5 | FALSE
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70 | 100 | FALSE
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66 | 94.4 | FALSE
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50 | 94.1 | FALSE
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15 | 76.5 | FALSE
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19 | 100 | FALSE
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57 | 94.4 | FALSE
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19 | 94.1 | FALSE
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4 | 76.5 | FALSE
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12 | 100 | FALSE
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3 | 94.4 | FALSE
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31 | 100 | FALSE
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27 | 94.4 | FALSE
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9 | 76.5 | FALSE
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84 | 100 | FALSE
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95 | 94.4 | FALSE
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99 | 94.1 | FALSE
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29 | 76.5 | FALSE
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48 | 100 | FALSE
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26 | 94.4 | FALSE
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39 | 94.1 | FALSE
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4 | 76.5 | FALSE
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13 | 100 | FALSE
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | 16.7 | TRUE
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16 | 94.4 | FALSE
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16 | 94.1 | FALSE
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46 | 94.4 | FALSE
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52 | 94.1 | FALSE
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18 | 76.5 | FALSE
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | 100 | FALSE
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | 94.4 | FALSE
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | 94.1 | FALSE
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | 76.5 | FALSE

## Exceptions
engagement_id | flag | triggers | situation | cause | recommended_action | decision_owner
5 | NEEDS REVIEW | fixed fee below the margin floor; margin failing, burn healthy | Fixed-fee engagement at -17.6% margin, against a floor of 15%. Margin is -17.6% while burn is 65.1% of the 2,690.0 hour ceiling. The two figures disagree and the data does not say which is the operative one. | not determinable from available data | Take the fixed-fee position to a scope and pricing conversation with the client before the 40 remaining contract days are used: decide whether remaining scope is delivered at the agreed fee, re-priced, or reduced. Engagement lead to decide, with the partner on the pricing question. | engagement lead
8 | RED | projected overrun, high confidence; burn above 90% with duration remaining | Projected overrun is 145.4% against a ceiling of 1,020.0 hours, at high projection confidence. Burn is 131.0% of a 1,020.0 hour ceiling with 254 of 542 contract days remaining. | not determinable from available data | Hours are 316.4 past the 1,020.0 hour ceiling with 254 contract days remaining. Decide whether to stop work at the ceiling or raise a change order for the remaining scope, and confirm the client position on the hours already delivered past it. Engagement lead to decide. | engagement lead
9 | RED | projected overrun, high confidence; burn above 90% with duration remaining | Projected overrun is 78.8% against a ceiling of 780.0 hours, at high projection confidence. Burn is 124.5% of a 780.0 hour ceiling with 71 of 291 contract days remaining. | not determinable from available data | Hours are 191.2 past the 780.0 hour ceiling with 71 contract days remaining. Decide whether to raise a change order or close out at the ceiling. Engagement lead to decide. | engagement lead
12 | NEEDS REVIEW | concentration above median fee | One person is 85.4% of hours on an engagement of 478,040, above the median fee. 2 people have logged time. | not determinable from available data | None. This trigger is a reason to look, not a decision to take. | engagement lead
20 | RED | projected overrun, high confidence | Projected overrun is 30.8% against a ceiling of 4,840.0 hours, at high projection confidence. | not determinable from available data | Projection at the current run rate exceeds the 4,840.0 hour ceiling by 30.8% with 228 contract days remaining. Decide whether the run rate is reduced, the scope trimmed, or a change order raised now rather than at the ceiling. Engagement lead to decide. | engagement lead
22 | RED | projected overrun, high confidence | Projected overrun is 11.1% against a ceiling of 1,520.0 hours, at high projection confidence. | not determinable from available data | Projection at the current run rate exceeds the 1,520.0 hour ceiling by 11.1% with 147 contract days remaining. Decide whether to re-plan the remaining scope or raise a change order. Engagement lead to decide. | engagement lead
25 | RED | no time logged for 14 days | No time has been logged for 24 days and the engagement is still active. Absent data is not evidence of completion. | not determinable from available data | Confirm with the delivery team whether work is ongoing and timesheets are outstanding, or whether delivery has in fact stopped; the absence of entries does not distinguish the two. Once known, decide whether the engagement status is changed. Engagement lead to decide. | engagement lead

## Data Quality
Record quality — entries in the period
Time entries in the period | 2774 | entry_count
Filed after the period closed | 160 | late_entries
Filed late, as a percentage | 5.8 | late_entry_pct
No billable flag set | 2 | null_billable
Redundant rows: same person, engagement, day and hours | 1 | suspected_duplicates
Distinct duplicate groups | 1 | duplicate_groups
Reporting coverage by week
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE
Data notes
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this workbook, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
engagement_id | projection_confidence | confidence_reason
25 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement