## Slide 1
Delivery and margin review
2026-08 · 18 active engagements · 11 clients
Generated 2026-08-27
Scoring model v1.0
Run delivery-review-2026-08-r1

## Slide 2
Portfolio summary
2026-08, active engagements, measured across the whole book
 | This period | Movement vs prior month
Active engagements | 18 | +0
Hours to date | 25,885.8 | +2,737.7
Ceiling hours | 44,390.0 | 
Portfolio burn | 58.3% | 
Revenue to date | 8,082,306 | 
Cost to date | 3,169,576 | 
Blended margin | 60.8% | -2.9pp
Mean health score | 83.4 | -1.3
In the green band | 13 of 18 | 
Blended margin is revenue less cost across the book, divided once. Fixed-price engagements take the fee as revenue; time and materials takes billable value at rate card.

## Slide 3
Margin by client
Blended across each client's active engagements, in percent
Chart: 
| Ashcombe Health Partners | Braemar Retail Corporation | Fernhollow Financial Trust | Lowmarsh Retail Partners | Merrivale Maritime Corporation | Northfield Municipal Group | Oakhaven Logistics Collective | Pentland Media Group | Quarrymoor Transit Partners | Stonebridge Energy Group | Thornbury Retail Partners
Margin % | 51 | 43.6 | 67.4 | 76.8 | 75.2 | 33.5 | 83.2 | -17.6 | 75 | 50.6 | 58.3
Lowest is Pentland Media Group at -17.6% across 1 engagement(s).

## Slide 4
Engagements at risk
8 of 10 engagements examined in detail, of 18 active
Engagement | Client | Burn | Margin | Health | Concentration | Ends
8 Regulatory Reporting Programme | Braemar Retail Corporation | 131.1% | 24.7% | 53.5 amber | 48.9% | 2027-05-12
9 Pricing Modernisation | Northfield Municipal Group | 124.5% | 33.5% | 59.5 amber | 54.1% | 2026-11-10
20 Inventory Implementation | Quarrymoor Transit Partners | 56.2% | 75.0% | 64.0 amber | 33.0% | 2027-04-16
22 Billing Platform Assessment | Fernhollow Financial Trust | 58.9% | 49.8% | 68.9 amber | 33.1% | 2027-01-25
5 Procurement Modernisation | Pentland Media Group | 65.1% | -17.6% | 69.0 amber | 24.8% | 2026-10-10
19 Grid Analytics Assessment | Thornbury Retail Partners | 86.9% | 51.6% | 76.6 green | 59.5% | 2026-10-10
25 Billing Platform Implementation | Stonebridge Energy Group | 80.6% | 50.2% | 76.6 green | 53.7% | 2026-10-25
15 Workforce Planning Programme | Ashcombe Health Partners | 76.1% | 50.7% | 94.4 green | 50.2% | 2026-10-16
Burn above 70% is amber and above 90% is red, the same thresholds the workbook applies. Ceilings are never re-baselined, so burn above 100% stays above 100%.

## Slide 5
RED · Regulatory Reporting Programme
Engagement 8 · Braemar Retail Corporation · fixed
Situation
Projected overrun is 146.6% against a ceiling of 1,020.0 hours, at high projection confidence. Burn is 131.1% of a 1,020.0 hour ceiling with 254 of 542 contract days remaining.
Burn | 131.1% | Margin | 24.7%
Hours to date | 1,337.7 | Ceiling hours | 1,020.0
Hours remaining | -317.6 | Projected overrun | 146.6%
Health | 53.5 | Band | amber
Cause
Not determinable from available data. The run rate is 0.8% below this engagement's own baseline, so the overrun is not the result of a recent acceleration in hours.
Recommended action
Engagement lead to take a scope and funding decision to Braemar Retail Corporation. Hours to date are 1,337.65 against a 1,020.0 hour ceiling with 254 contract days still to run; the decision needed is whether the remaining scope is funded, and by what instrument. The ceiling is not to be re-baselined.
Decision owner: engagement lead

## Slide 6
RED · Pricing Modernisation
Engagement 9 · Northfield Municipal Group · fixed
Situation
Projected overrun is 78.8% against a ceiling of 780.0 hours, at high projection confidence. Burn is 124.5% of a 780.0 hour ceiling with 71 of 291 contract days remaining.
Burn | 124.5% | Margin | 33.5%
Hours to date | 971.2 | Ceiling hours | 780.0
Hours remaining | -191.2 | Projected overrun | 78.8%
Health | 59.5 | Band | amber
Cause
Not determinable from available data. The run rate is 12.5% above this engagement's own baseline of 37.08 hours per week.
Recommended action
Engagement lead to take a change order or stop-work decision to Northfield Municipal Group. Hours to date are 971.2 against a 780.0 hour ceiling with 71 contract days remaining. The ceiling is not to be re-baselined.
Decision owner: engagement lead

## Slide 7
RED · Inventory Implementation
Engagement 20 · Quarrymoor Transit Partners · fixed
Situation
Projected overrun is 30.8% against a ceiling of 4,840.0 hours, at high projection confidence.
Burn | 56.2% | Margin | 75.0%
Hours to date | 2,720.7 | Ceiling hours | 4,840.0
Hours remaining | 2,119.3 | Projected overrun | 30.8%
Health | 64.0 | Band | amber
Cause
Not determinable from available data. Burn is 56.2% and the run rate is 17.8% above this engagement's own baseline of 94.00 hours per week, with 228 contract days remaining.
Recommended action
Engagement lead to decide, with Quarrymoor Transit Partners, whether the current run rate of 110.78 hours per week is the delivery plan for the remaining 228 contract days or an overrun in progress. Projected total is 6,328.8 hours against a 4,840.0 hour ceiling.
Decision owner: engagement lead

## Slide 8
Data quality and caveats
2026-08, across the whole firm
Record quality | Count
Time entries in the period | 2,774
Filed after the period closed | 160 (5.8%)
No billable flag set | 2
Redundant rows: same person, engagement, day and hours | 1
Reporting coverage
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this pack, and delivery for the week cannot be measured from the data.
Projections reported with low confidence
Engagement 25: 2 of the trailing 4 readable weeks have no time logged against this engagement
Figures come from the BizData tools and are reproduced in engagement-book-2026-08.xlsx. Scoring model v1.0.