## Summary
Delivery and margin review
Period | 2026-08
Run id | delivery-review-2026-08-r1
Scoring model version | v1.0
Portfolio
Engagements in the book
Examined in detail
Ceiling hours
Hours to date
Ceiling amount
Over their ceiling
Above 70% burn
Not in the green band
Above 70% person concentration
Projections reported low confidence
Exceptions raised
Portfolio, as the tools measured it
Active engagements | 18
Clients | 11
In the green band | 13
Ceiling hours | 44390
Hours to date | 25885.85
Portfolio burn | 58.3
Revenue to date | 8082306.13
Cost to date | 3169576.2
Blended margin | 60.8
Mean health score | 83.4
Blended margin, movement vs prior month | -2.9
Mean health score, movement vs prior month | -1.3
Hours to date, movement vs prior month | 2737.7
Reporting coverage
Weeks below the coverage floor | 1
Lowest weekly reporting coverage | 16.7

## Engagements
engagement_id | client_name | name | sow_ref | fee_type | status | start_date | end_date | days_remaining | ceiling_hours | hours_to_date | burn_pct | ceiling_amount | person_concentration_pct | people_count | health_score | health_band | score_delta_vs_prior_period | top_risk_factor | examined | hours_remaining | weekly_run_rate_4wk | weeks_counted | weeks_with_no_hours | projected_total_hours | projected_overrun_pct | projection_confidence | confidence_reason | run_rate_vs_baseline_pct | days_since_last_entry | late_entry_pct | invoiced | paid | wip_unbilled | cost_to_date | billable_value_to_date | margin_pct | realisation_pct | dso_days | dso_baseline_days | payment_behaviour_change_pct
2 | Oakhaven Logistics Collective | Credit Risk Migration | SOW-2026-002 | fixed | active | 2026-01-28 | 2026-08-21 | 0 | 1980 | 575.9 |  | 420591.6 | 55.5 | 3 | 99.7 | green | -0.3 | payment_behaviour | yes | 1404.1 | 17.55 | 4 | 0 | 575.9 |  | high | 4 readable weeks with time logged in every one, 0.0% of entries filed after the period closed | -32 | 0 | 0 | 280394.4 | 280394.4 | -156504.3 | 70481.3 | 123890.1 |  | 86.8 | 29.5 | 29 | 1.7
3 | Ashcombe Health Partners | Revenue Assurance Optimisation | SOW-2026-003 | time_and_materials | active | 2026-01-09 | 2026-10-31 | 61 | 940 | 642.1 |  | 232180 | 46.2 | 3 | 98.3 | green | -0.9 | burn_trajectory | no
5 | Pentland Media Group | Procurement Modernisation | SOW-2026-005 | fixed | active | 2026-01-31 | 2026-10-10 | 40 | 2690 | 1751.5 |  | 133038.43 | 24.8 | 5 | 69 | amber | -11.2 | margin | yes | 938.5 | 68.88 | 4 | 0 | 2145.1 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 37.2 | 0 | 3.4 | 83149.02 | 49889.41 | 247112.18 | 156515.8 | 330261.2 |  | 87 | 44 | 41.1 | 6.9
7 | Braemar Retail Corporation | Revenue Assurance Discovery | SOW-2026-007 | time_and_materials | active | 2026-02-19 | 2027-02-27 | 180 | 1480 | 672.5 |  | 393680 | 45 | 3 | 100 | green | 31.2 |  | no
8 | Braemar Retail Corporation | Regulatory Reporting Programme | SOW-2025-008 | fixed | active | 2025-11-16 | 2027-05-12 | 254 | 1020 | 1337.65 |  | 274176 | 48.9 | 4 | 53.5 | amber | -3.8 | burn_trajectory | yes | -317.65 | 32.46 | 4 | 0 | 2515.6 |  | high | 4 readable weeks with time logged in every one, 2.1% of entries filed after the period closed | -0.8 | 3 | 2.1 | 42180.92 | 42180.92 | 351443.43 | 206451.55 | 393624.35 |  | 90 | 24.3 | 25.3 | -4
9 | Northfield Municipal Group | Pricing Modernisation | SOW-2026-009 | fixed | active | 2026-01-23 | 2026-11-10 | 71 | 780 | 971.2 |  | 241737.6 | 54.1 | 2 | 59.5 | amber | -5.5 | burn_trajectory | yes | -191.2 | 41.73 | 4 | 0 | 1394.4 |  | high | 4 readable weeks with time logged in every one, 3.1% of entries filed after the period closed | 12.5 | 0 | 3.1 | 136634.29 | 136634.29 | 172915.71 | 160725.6 | 309550 |  | 87 | 32.8 | 31.3 | 4.5
11 | Lowmarsh Retail Partners | Inventory Modernisation | SOW-2025-011 | fixed | active | 2025-10-11 | 2027-05-02 | 244 | 4940 | 2821 |  | 1332713.2 | 44.7 | 3 | 73.1 | green | -6.6 | burn_trajectory | no
12 | Stonebridge Energy Group | Credit Risk Programme | SOW-2026-012 | time_and_materials | active | 2026-01-14 | 2026-09-24 | 24 | 1480 | 999.65 |  | 478040 | 85.4 | 2 | 99.9 | green | 0.4 | payment_behaviour | yes | 480.35 | 34.34 | 4 | 0 | 1117.4 |  | high | 4 readable weeks with time logged in every one, 9.9% of entries filed after the period closed | 2.3 | 0 | 9.9 | 261087.5 | 207099.5 | 22301 | 138350.2 | 283388.5 |  | 88.7 | 39.8 | 39.7 | 0.4
13 | Ashcombe Health Partners | Payments Assessment | SOW-2025-013 | time_and_materials | active | 2025-09-28 | 2026-12-08 | 99 | 3200 | 2097.5 |  | 812800 | 63.6 | 3 | 89.1 | green | -0.2 | burn_trajectory | no
15 | Ashcombe Health Partners | Workforce Planning Programme | SOW-2025-015 | time_and_materials | active | 2025-11-04 | 2026-10-16 | 46 | 3540 | 2694.5 |  | 1069080 | 50.2 | 4 | 94.4 | green | 10.2 | burn_trajectory | yes | 845.5 | 71.18 | 4 | 0 | 3162.2 |  | high | 4 readable weeks with time logged in every one, 6.5% of entries filed after the period closed | -21.2 | 0 | 6.5 | 453254.3 | 372346 | 98811.1 | 272353.4 | 552065.4 |  | 88.8 | 36.7 | 35.5 | 3.4
16 | Braemar Retail Corporation | Field Operations Rollout | SOW-2025-016 | time_and_materials | active | 2025-09-01 | 2027-03-09 | 190 | 7980 | 2552.1 |  | 1955100 | 41.7 | 3 | 100 | green | 0.2 |  | no
18 | Thornbury Retail Partners | Payments Modernisation | SOW-2025-018 | fixed | active | 2025-12-04 | 2026-12-04 | 95 | 820 | 564.5 |  | 217906.8 | 53.2 | 3 | 94.1 | green | -5.7 | burn_trajectory | no
19 | Thornbury Retail Partners | Grid Analytics Assessment | SOW-2025-019 | time_and_materials | active | 2025-12-03 | 2026-10-10 | 40 | 940 | 816.8 |  | 262260 | 59.5 | 2 | 76.6 | green | -12.2 | burn_trajectory | yes | 123.2 | 29.88 | 4 | 0 | 987.5 |  | high | 4 readable weeks with time logged in every one, 7.5% of entries filed after the period closed | 36.3 | 0 | 7.5 | 189126.6 | 189126.6 | 30225 | 106100 | 219351.6 |  | 86.4 | 29.7 | 30.8 | -3.7
20 | Quarrymoor Transit Partners | Inventory Implementation | SOW-2025-020 | fixed | active | 2025-11-30 | 2027-04-16 | 228 | 4840 | 2720.7 |  | 1154243.2 | 33 | 6 | 64 | amber | 0.8 | burn_trajectory | yes | 2119.3 | 110.78 | 4 | 0 | 6328.8 |  | high | 4 readable weeks with time logged in every one, 7.8% of entries filed after the period closed | 17.8 | 0 | 7.8 | 355151.75 | 355151.75 | 255780.05 | 288157 | 610931.8 |  | 89.1 | 55 | 51.7 | 6.5
22 | Fernhollow Financial Trust | Billing Platform Assessment | SOW-2026-022 | time_and_materials | active | 2026-02-19 | 2027-01-25 | 147 | 1520 | 895.2 |  | 443840 | 33.1 | 4 | 68.9 | amber | -7.2 | burn_trajectory | yes | 624.8 | 37.78 | 4 | 0 | 1688.5 |  | high | 4 readable weeks with time logged in every one, 3.4% of entries filed after the period closed | 3.3 | 0 | 3.4 | 197232.6 | 110441.3 | 31998.2 | 115100.6 | 229230.8 |  | 90.9 | 46.2 | 44.1 | 4.7
23 | Fernhollow Financial Trust | Asset Register Assessment | SOW-2025-023 | fixed | active | 2025-12-30 | 2027-01-11 | 133 | 1840 | 695.4 |  | 455731.2 | 55.7 | 2 | 99.3 | green | -0.7 | payment_behaviour | no
25 | Stonebridge Energy Group | Billing Platform Implementation | SOW-2025-025 | time_and_materials | active | 2025-11-11 | 2026-10-25 | 55 | 2440 | 1967.8 |  | 688080 | 53.7 | 3 | 76.6 | green | -9.4 | reporting_gap | yes | 472.2 | 22.53 | 4 | 2 | 2144.8 |  | low | 2 of the trailing 4 readable weeks have no time logged against this engagement | -46.6 | 24 | 0 | 441859 | 403089 | 8091.5 | 224191.7 | 449950.5 |  | 87.4 | 39.8 | 39.7 | 0.4
29 | Merrivale Maritime Corporation | Grid Analytics Integration | SOW-2026-029 | fixed | active | 2026-01-26 | 2026-12-26 | 117 | 1960 | 1109.85 |  | 482904.8 | 37.1 | 5 | 85.2 | green | -1.6 | burn_trajectory | no

## Time Detail
engagement_id | engagement_name | week_start | hours | billable_hours | cost | billable_value | entry_count | pct_active_reporting | firm_wide_gap
2 | Credit Risk Migration | 2026-08-03 | 10 | 7.8 | 1157.1 | 1974.2 | 11 | 100 | FALSE
2 | Credit Risk Migration | 2026-08-17 | 23.9 | 21.6 | 2865.5 | 5359.6 | 22 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-03 | 19.8 | 19.5 | 3060.9 | 6409.1 | 17 | 100 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-17 | 15.4 | 15.4 | 2522.2 | 5498.4 | 11 | 94.4 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-24 | 25.7 | 23 | 3395.1 | 6896.5 | 24 | 94.1 | FALSE
3 | Revenue Assurance Optimisation | 2026-08-31 | 7 | 6.6 | 1097 | 2276.3 | 7 | 76.5 | FALSE
5 | Procurement Modernisation | 2026-08-03 | 40.8 | 35.1 | 4130.5 | 7844 | 37 | 100 | FALSE
5 | Procurement Modernisation | 2026-08-10 | 214.7 | 187.1 | 22176.3 | 45110.1 | 186 | 16.7 | TRUE
5 | Procurement Modernisation | 2026-08-17 | 65 | 47.6 | 6377.2 | 10605.3 | 51 | 94.4 | FALSE
5 | Procurement Modernisation | 2026-08-24 | 95.9 | 91 | 9038.2 | 20318 | 86 | 94.1 | FALSE
5 | Procurement Modernisation | 2026-08-31 | 19.1 | 14.4 | 1878.2 | 3463 | 17 | 76.5 | FALSE
7 | Revenue Assurance Discovery | 2026-08-03 | 8.8 | 8.8 | 1612.6 | 3230.7 | 10 | 100 | FALSE
7 | Revenue Assurance Discovery | 2026-08-17 | 24.5 | 21.8 | 3588.2 | 6875.4 | 22 | 94.4 | FALSE
7 | Revenue Assurance Discovery | 2026-08-24 | 35.5 | 31.4 | 5005 | 9676.6 | 27 | 94.1 | FALSE
7 | Revenue Assurance Discovery | 2026-08-31 | 6.7 | 4 | 442.2 | 564 | 4 | 76.5 | FALSE
8 | Regulatory Reporting Programme | 2026-08-03 | 19 | 18.4 | 1591.3 | 3403.9 | 23 | 100 | FALSE
8 | Regulatory Reporting Programme | 2026-08-17 | 51.7 | 43.2 | 8426.5 | 14753.9 | 49 | 94.4 | FALSE
8 | Regulatory Reporting Programme | 2026-08-24 | 25.8 | 25.8 | 4543.6 | 9490.6 | 22 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-03 | 43.7 | 36 | 7559 | 13790.8 | 35 | 100 | FALSE
9 | Pricing Modernisation | 2026-08-17 | 22.4 | 17.9 | 3943.2 | 7081.6 | 19 | 94.4 | FALSE
9 | Pricing Modernisation | 2026-08-24 | 46.9 | 38.7 | 7416.6 | 13622.4 | 40 | 94.1 | FALSE
9 | Pricing Modernisation | 2026-08-31 | 3.9 | 2.2 | 460.2 | 633.6 | 3 | 76.5 | FALSE
11 | Inventory Modernisation | 2026-08-03 | 56.9 | 48.1 | 5968.5 | 12270.6 | 52 | 100 | FALSE
11 | Inventory Modernisation | 2026-08-10 | 108.5 | 100.1 | 12964.7 | 28680.3 | 106 | 16.7 | TRUE
11 | Inventory Modernisation | 2026-08-17 | 80.5 | 67.1 | 8698.5 | 17802.3 | 67 | 94.4 | FALSE
11 | Inventory Modernisation | 2026-08-24 | 87 | 72.3 | 9917.5 | 19833 | 82 | 94.1 | FALSE
11 | Inventory Modernisation | 2026-08-31 | 12.8 | 11.8 | 1217.9 | 2793.9 | 12 | 76.5 | FALSE
12 | Credit Risk Programme | 2026-08-03 | 20 | 18.9 | 2560 | 5481 | 17 | 100 | FALSE
12 | Credit Risk Programme | 2026-08-17 | 16.3 | 15.7 | 2086.4 | 4553 | 16 | 94.4 | FALSE
12 | Credit Risk Programme | 2026-08-24 | 35.9 | 32.7 | 4733.2 | 9729.5 | 29 | 94.1 | FALSE
12 | Credit Risk Programme | 2026-08-31 | 7 | 5.8 | 1106 | 2175 | 9 | 76.5 | FALSE
13 | Payments Assessment | 2026-08-03 | 61.4 | 52.6 | 5596.6 | 11399.7 | 58 | 100 | FALSE
13 | Payments Assessment | 2026-08-17 | 66.6 | 59 | 7144.4 | 15000.7 | 60 | 94.4 | FALSE
13 | Payments Assessment | 2026-08-24 | 66.6 | 53.5 | 7449 | 14711.6 | 57 | 94.1 | FALSE
13 | Payments Assessment | 2026-08-31 | 10 | 7.8 | 1021 | 1953.9 | 10 | 76.5 | FALSE
14 | Asset Register Programme | 2026-08-03 | 49.8 | 41.9 | 5251.4 | 10399.6 | 46 | 100 | FALSE
14 | Asset Register Programme | 2026-08-17 | 74 | 69.4 | 8086 | 17357.4 | 70 | 94.4 | FALSE
14 | Asset Register Programme | 2026-08-24 | 55.6 | 50.5 | 5092.9 | 11234.6 | 45 | 94.1 | FALSE
14 | Asset Register Programme | 2026-08-31 | 19.3 | 16.5 | 2507.5 | 4721.4 | 16 | 76.5 | FALSE
15 | Workforce Planning Programme | 2026-08-03 | 73.8 | 65.9 | 7883.1 | 15012 | 70 | 100 | FALSE
15 | Workforce Planning Programme | 2026-08-17 | 84 | 73.3 | 9353.9 | 17160.7 | 66 | 94.4 | FALSE
15 | Workforce Planning Programme | 2026-08-24 | 55.8 | 52 | 5863.5 | 11338 | 50 | 94.1 | FALSE
15 | Workforce Planning Programme | 2026-08-31 | 14.9 | 14.6 | 1515.6 | 3141.9 | 15 | 76.5 | FALSE
16 | Field Operations Rollout | 2026-08-03 | 20.8 | 16.6 | 2788.4 | 4531.3 | 19 | 100 | FALSE
16 | Field Operations Rollout | 2026-08-17 | 64.2 | 55.7 | 9819.4 | 18259.1 | 57 | 94.4 | FALSE
16 | Field Operations Rollout | 2026-08-24 | 20.1 | 16.1 | 2972.1 | 5155.5 | 19 | 94.1 | FALSE
16 | Field Operations Rollout | 2026-08-31 | 3.5 | 3.5 | 262.5 | 731.5 | 4 | 76.5 | FALSE
18 | Payments Modernisation | 2026-08-03 | 16 | 14.8 | 2736 | 4854.4 | 12 | 100 | FALSE
18 | Payments Modernisation | 2026-08-17 | 2.2 | 2.2 | 257.2 | 522.8 | 3 | 94.4 | FALSE
18 | Payments Modernisation | 2026-08-24 | 31.4 | 27.6 | 3827.2 | 6869.8 | 31 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-03 | 29 | 26.2 | 3920 | 8545.8 | 31 | 100 | FALSE
19 | Grid Analytics Assessment | 2026-08-17 | 25.9 | 23.4 | 3526 | 7476.2 | 27 | 94.4 | FALSE
19 | Grid Analytics Assessment | 2026-08-24 | 39.6 | 36 | 5412 | 11721.4 | 39 | 94.1 | FALSE
19 | Grid Analytics Assessment | 2026-08-31 | 9.6 | 7.5 | 1266 | 2481.6 | 9 | 76.5 | FALSE
20 | Inventory Implementation | 2026-08-03 | 91.7 | 85.9 | 9577.6 | 21654.1 | 84 | 100 | FALSE
20 | Inventory Implementation | 2026-08-17 | 98.2 | 89.5 | 9170.1 | 20439.7 | 95 | 94.4 | FALSE
20 | Inventory Implementation | 2026-08-24 | 123.2 | 108.6 | 11807.8 | 25786.6 | 99 | 94.1 | FALSE
20 | Inventory Implementation | 2026-08-31 | 32 | 27.5 | 3631 | 7521.4 | 29 | 76.5 | FALSE
22 | Billing Platform Assessment | 2026-08-03 | 45.8 | 40.2 | 5904.4 | 11817.8 | 48 | 100 | FALSE
22 | Billing Platform Assessment | 2026-08-17 | 28.2 | 27.3 | 3352.7 | 7140.7 | 26 | 94.4 | FALSE
22 | Billing Platform Assessment | 2026-08-24 | 40.7 | 39.4 | 5247.5 | 11074.1 | 39 | 94.1 | FALSE
22 | Billing Platform Assessment | 2026-08-31 | 4.2 | 4.2 | 936.6 | 1965.6 | 4 | 76.5 | FALSE
23 | Asset Register Assessment | 2026-08-03 | 17.2 | 16.5 | 2516.2 | 5072.1 | 13 | 100 | FALSE
23 | Asset Register Assessment | 2026-08-10 | 87 | 80.2 | 12103.1 | 24097 | 69 | 16.7 | TRUE
23 | Asset Register Assessment | 2026-08-17 | 13.7 | 12.5 | 2356.4 | 4312.5 | 16 | 94.4 | FALSE
23 | Asset Register Assessment | 2026-08-24 | 19.4 | 16.1 | 2566.3 | 4473.5 | 16 | 94.1 | FALSE
25 | Billing Platform Implementation | 2026-08-03 | 33.9 | 28.3 | 4500.8 | 8091.5 | 32 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-03 | 22.2 | 21 | 2579.4 | 5375.7 | 23 | 100 | FALSE
29 | Grid Analytics Integration | 2026-08-17 | 57.5 | 49.8 | 6358.1 | 11510.6 | 46 | 94.4 | FALSE
29 | Grid Analytics Integration | 2026-08-24 | 62.7 | 60.2 | 7159.7 | 14644.7 | 52 | 94.1 | FALSE
29 | Grid Analytics Integration | 2026-08-31 | 13.6 | 13.3 | 1572.8 | 3149.3 | 18 | 76.5 | FALSE
30 | Asset Register Migration | 2026-08-03 | 46.3 | 38.4 | 4946.6 | 9630.7 | 43 | 100 | FALSE
30 | Asset Register Migration | 2026-08-17 | 62.2 | 54.8 | 6783.9 | 13660.2 | 54 | 94.4 | FALSE
30 | Asset Register Migration | 2026-08-24 | 31.5 | 26.4 | 2853.6 | 5657.6 | 30 | 94.1 | FALSE
30 | Asset Register Migration | 2026-08-31 | 11.2 | 6.8 | 919.2 | 1306.5 | 11 | 76.5 | FALSE

## Exceptions
engagement_id | flag | triggers | situation | cause | recommended_action | decision_owner
5 | NEEDS REVIEW | fixed fee below the margin floor; margin failing, burn healthy | Fixed-fee engagement at -17.6% margin, against a floor of 15%. Margin is -17.6% while burn is 65.1% of the 2,690.0 hour ceiling. The two figures disagree and the data does not say which is the operative one. | Not determinable from available data. Cost to date is 156,515.80 against a ceiling amount of 133,038.43, while burn is 65.1% of the 2,690.0 hour ceiling. Whether the fee was set below delivery cost at signing or the cost base has moved since is not in the data. | Engagement lead to establish which of the two figures is operative before the next invoice to Pentland Media Group, and to decide whether to raise a change order over the remaining 40 contract days or to absorb the shortfall. The ceiling is not to be re-baselined. | engagement lead
8 | RED | projected overrun, high confidence; burn above 90% with duration remaining | Projected overrun is 146.6% against a ceiling of 1,020.0 hours, at high projection confidence. Burn is 131.1% of a 1,020.0 hour ceiling with 254 of 542 contract days remaining. | Not determinable from available data. The run rate is 0.8% below this engagement's own baseline, so the overrun is not the result of a recent acceleration in hours. | Engagement lead to take a scope and funding decision to Braemar Retail Corporation. Hours to date are 1,337.65 against a 1,020.0 hour ceiling with 254 contract days still to run; the decision needed is whether the remaining scope is funded, and by what instrument. The ceiling is not to be re-baselined. | engagement lead
9 | RED | projected overrun, high confidence; burn above 90% with duration remaining | Projected overrun is 78.8% against a ceiling of 780.0 hours, at high projection confidence. Burn is 124.5% of a 780.0 hour ceiling with 71 of 291 contract days remaining. | Not determinable from available data. The run rate is 12.5% above this engagement's own baseline of 37.08 hours per week. | Engagement lead to take a change order or stop-work decision to Northfield Municipal Group. Hours to date are 971.2 against a 780.0 hour ceiling with 71 contract days remaining. The ceiling is not to be re-baselined. | engagement lead
12 | NEEDS REVIEW | concentration above median fee | One person is 85.4% of hours on an engagement of 478,040, above the median fee. 2 people have logged time. | Not determinable from available data. 2 people have logged time and one of them is 85.4% of hours; whether that is a continuity risk depends on leave, client preference and staffing offers, none of which is in the data. | None. This trigger is a reason to look, not a decision to take. | engagement lead
20 | RED | projected overrun, high confidence | Projected overrun is 30.8% against a ceiling of 4,840.0 hours, at high projection confidence. | Not determinable from available data. Burn is 56.2% and the run rate is 17.8% above this engagement's own baseline of 94.00 hours per week, with 228 contract days remaining. | Engagement lead to decide, with Quarrymoor Transit Partners, whether the current run rate of 110.78 hours per week is the delivery plan for the remaining 228 contract days or an overrun in progress. Projected total is 6,328.8 hours against a 4,840.0 hour ceiling. | engagement lead
22 | RED | projected overrun, high confidence | Projected overrun is 11.1% against a ceiling of 1,520.0 hours, at high projection confidence. | Not determinable from available data. The run rate is 3.3% above this engagement's own baseline of 36.56 hours per week. | Engagement lead to decide whether to hold the current run rate or re-plan the remaining 147 contract days with Fernhollow Financial Trust. Projected total is 1,688.5 hours against a 1,520.0 hour ceiling. | engagement lead
25 | RED | no time logged for 14 days | No time has been logged for 24 days and the engagement is still active. Absent data is not evidence of completion. | Not determinable from available data. The last entry is dated 2026-08-07 and 2 of the trailing 4 readable weeks have no time logged against this engagement, which is why projection confidence is low. Absent data is not evidence of completion. | Engagement lead to confirm with the delivery team and Stonebridge Energy Group whether work is continuing and unfiled or has paused, and to have the outstanding timesheets filed before the September review. Status is not to be changed on the basis of absent entries. | engagement lead

## Data Quality
Record quality — entries in the period
Time entries in the period | 2774 | entry_count
Filed after the period closed | 160 | late_entries
Filed late, as a percentage | 5.8 | late_entry_pct
No billable flag set | 2 | null_billable
Redundant rows: same person, engagement, day and hours | 1 | suspected_duplicates
Distinct duplicate groups | 1 | duplicate_groups
Reporting coverage by week
week_start | week_end | engagements_active | engagements_reporting | pct_active_reporting | firm_wide_gap
2026-07-27 | 2026-08-02 | 18 | 18 | 100 | FALSE
2026-08-03 | 2026-08-09 | 18 | 18 | 100 | FALSE
2026-08-10 | 2026-08-16 | 18 | 3 | 16.7 | TRUE
2026-08-17 | 2026-08-23 | 18 | 17 | 94.4 | FALSE
2026-08-24 | 2026-08-30 | 17 | 16 | 94.1 | FALSE
2026-08-31 | 2026-09-06 | 17 | 13 | 76.5 | FALSE
Data notes
Week of 2026-08-10: 16.7% of active engagements filed time, below the 60% coverage floor. This week is a filing artifact. It is excluded from every run rate and projection in this workbook, and delivery for the week cannot be measured from the data.
Not all of the change since the previous pack could be itemised. 3 entries added, of which only 0 arrived after the previous watermark. The rest were filed with an earlier timestamp and cannot be listed. Entries filed with a timestamp earlier than the previous run's, amendments to existing records and deletions do not appear in the list above.
Projections reported with low confidence
engagement_id | projection_confidence | confidence_reason
25 | low | 2 of the trailing 4 readable weeks have no time logged against this engagement